## QuickStartGuide
C-100 (2026)
Updated June 2025
Quick Start Guide
GENERAL INFORMATION
1) The intended use of the C-100 (2026) is to enable project managers to communicate their project cost estimates to budget officers in the standard format required for capital project budget requests/submittals to OFM.
2) This workbook is protected so that the worksheets within it cannot be moved or deleted in the usual manner. This protection is necessary to ensure that the cost estimate details and formulas align with the estimating application in the Capital Budgeting System.
3) The estimating format to develop the maximum allowable construction cost (MACC) is presented in Uniformat II.
4) Form-calculated costs such as A/E Basic Design Service fees and Agency Project Management costs are dependent on other estimated project costs such as MACC, equipment, etc.
5) Project estimates generated with this tool are not sufficient for budget request submittals to OFM. Use the Capital Budgeting System to submit capital project budget requests and attach the C-100 form.
6) Contact your assigned OFM Capital Budget Analyst with questions.
OFM Capital Budget Analyst
INSTRUCTIONS
1) Only green cells are available for data entry.
2) Fill in all known cells in the 'Summary' tab prior to moving on to the cost entry tabs A-G.
3) It is recommended, but not required, to fill out cost entry tabs in the following order:
A. Acquisition, C. Construction Contracts, D. Equipment, G. Other Costs, B. Consultant Services, F. Project Management, then E. Artwork.
4) If additional rows are inserted to capture additional project costs, a description must be provided in the Notes column or within Tab H. Additional Notes. Be particularly detailed for additional costs estimated for contingencies and project management.
FORM-CALCULATED COSTS (FEE CALCULATIONS)
1) A/E Basic Design Services: AE Fee % (x) (MACC or TCC + Contingency)
2) Design Services Contingency: Contingency % (x) Consultant Services Subtotal
3) Construction Contingency: Contingency % (x) MACC or TCC
4) Artwork: 0.5% (x) Total Project Cost
5) Agency Project Management (Greater than $1 million): (AE Fee % - 3%) (x) (Acquisition Total + Consultant Services Total + MACC + Construction Contingency + Other Costs)

## Summary
STATE OF WASHINGTON
AGENCY / INSTITUTION PROJECT COST SUMMARY
Updated June 2025
Agency
Project Name
OFM Project Number
Contact Information
Name
Phone Number
Email
Statistics
Gross Square Feet |  | MACC per Gross Square Foot
Usable Square Feet |  | Escalated MACC per Gross Square Foot
Alt Gross Unit of Measure
Space Efficiency |  | A/E Fee Class | A
Construction Type | Courthouses | A/E Fee Percentage | 16.51%
Remodel | No | Projected Life of Asset (Years)
Additional Project Details
Procurement Approach | GCCM | Art Requirement Applies
Inflation Rate | 3.16% | Higher Ed Institution
Sales Tax Rate % | 10% | Location Used for Tax Rate
Contingency Rate | 5%
Base Month (Estimate Date) | 2024-09-20 11:31 | OFM UFI# (from FPMT, if available)
Project Administered By
Schedule
Predesign Start | 2025-09-01 | Predesign End | 2025-09-01
Design Start | 2026-09-01 | Design End | 2030-09-01
Construction Start | 2030-09-01 | Construction End | 2031-09-01
Construction Duration | 12
Green cells must be filled in by user
Project Cost Summary
Total Project | 0 | Total Project Escalated | 0
|  | Rounded Escalated Total | 0
Amount funded in Prior Biennia |  |  | 0
Amount in current Biennium |  |  | 0
Next Biennium |  |  | 0
Out Years |  |  | 0
Acquisition
Acquisition Subtotal | 0 | Acquisition Subtotal Escalated | 0
Consultant Services
Predesign Services | 0
Design Phase Services | 0
Extra Services | 0
Other Services | 0
Design Services Contingency | 0
Consultant Services Subtotal | 0 | Consultant Services Subtotal Escalated | 0
Construction
Maximum Allowable Construction Cost (MACC) | 0 | Maximum Allowable Construction Cost (MACC) Escalated | 0
GCCM Risk Contingencies | 0 |  | 0
GCCM Management | 0 |  | 0
Owner Construction Contingency | 0 |  | 0
Non-Taxable Items | 0 |  | 0
Sales Tax | 0 | Sales Tax Escalated | 0
Construction Subtotal | 0 | Construction Subtotal Escalated | 0
Equipment
Equipment | 0
Sales Tax | 0
Non-Taxable Items | 0
Equipment Subtotal | 0 | Equipment Subtotal Escalated | 0
Artwork
Artwork Subtotal | 0 | Artwork Subtotal Escalated | 0
Agency Project Administration
Agency Project Administration Subtotal | 0
DES Additional Services Subtotal | 0
Other Project Admin Costs | 0
Project Administration Subtotal | 0 | Project Administration Subtotal Escalated | 0
Other Costs
Other Costs Subtotal | 0 | Other Costs Subtotal Escalated | 0
Project Cost Estimate
Total Project | 0 | Total Project Escalated | 0
|  | Rounded Escalated Total | 0

## Biennium Summary
Funding Summary
Current Biennium
| Project Cost (Escalated) | Funded in Prior Biennia | 2025-2027 | 2027-2029 | Out Years
Acquisition
Acquisition Subtotal | 0 |  |  |  | 0
Consultant Services
Consultant Services Subtotal | 0 |  |  |  | 0
Construction
Construction Subtotal | 0 |  |  |  | 0
Equipment
Equipment Subtotal | 0 |  |  |  | 0
Artwork
Artwork Subtotal | 0 |  |  |  | 0
Agency Project Administration
Project Administration Subtotal | 0 |  |  |  | 0
Other Costs
Other Costs Subtotal | 0 |  |  |  | 0
Project Cost Estimate
Total Project | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| Percentage requested as a new appropriation |  | NA
What is planned for the requested new appropriation? (Ex. Acquisition and design, phase 1 construction, etc.)
Insert Row Here
What has been completed or is underway with a previous appropriation?
Insert Row Here
What is planned with a future appropriation?
Insert Row Here

## Basis of Estimate (hidden)
C-100(2021)
Basis of Estimate
Scope of work: Brief description of project
Function, size, number of storys, character, quality
Insert Row Here
Site Conditions: Brief summary of key site factors influencing cost
Site constraints, congestion, site access, topography, ground conditions
Insert Row Here
Construction Conditions: Brief summary of key construction operations influencing cost
Working hours, noise/dust, other users, ease of access
Insert Row Here
Market Conditions: Brief summary of key bidding factors influencing cost
Availability of labor, market hunger, market readiness
Insert Row Here
Major Risks
1
2
3
4
5
6
7
8
9
10
Insert Row Here
Exclusions: Major cost items excluded from the project
Insert Row Here
Other Comments
Insert Row Here

## A. Acquisition
Cost Estimate Details
Acquisition Costs
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
Purchase/Lease
Appraisal and Closing
Right of Way
Demolition
Pre-Site Development
Other
Insert Row Here
ACQUISITION TOTAL | 0 | NA | 0
Green cells must be filled in by user

## B. Consultant Services
Cost Estimate Details
Consultant Services
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
1) Pre-Schematic Design Services
Programming/Site Analysis
Environmental Analysis
Predesign Study
Other
Insert Row Here
Sub TOTAL | 0 | 1.0624 | 0 | Escalated to Design Start
2) Construction Documents
A/E Basic Design Services | 0 |  |  | 69% of A/E Basic Services
Other
Insert Row Here
Sub TOTAL | 0 | 1.1307 | 0 | Escalated to Mid-Design
3) Extra Services
Civil Design (Above Basic Svcs)
Geotechnical Investigation
Commissioning
Site Survey
Testing
LEED Services
Voice/Data Consultant
Value Engineering
Constructability Review
Environmental Mitigation (EIS)
Landscape Consultant
Other
Insert Row Here
Sub TOTAL | 0 | 1.1307 | 0 | Escalated to Mid-Design
4) Other Services
Bid/Construction/Closeout | 0 |  |  | 31% of A/E Basic Services
HVAC Balancing
Staffing
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0 | Escalated to Mid-Const.
5) Design Services Contingency
Design Services Contingency | 0
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0 | Escalated to Mid-Const.
CONSULTANT SERVICES TOTAL | 0 |  | 0
Green cells must be filled in by user

## C. Construction Contracts
Cost Estimate Details
Construction Contracts
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
1) Site Work
G10 - Site Preparation
G20 - Site Improvements
G30 - Site Mechanical Utilities
G40 - Site Electrical Utilities
G60 - Other Site Construction
Other
Insert Row Here
Sub TOTAL | 0 | 1.2033 | 0
2) Related Project Costs
Offsite Improvements
City Utilities Relocation
Parking Mitigation
Stormwater Retention/Detention
Other
Insert Row Here
Sub TOTAL | 0 | 1.2033 | 0
3) Facility Construction
A10 - Foundations
A20 - Basement Construction
B10 - Superstructure
B20 - Exterior Closure
B30 - Roofing
C10 - Interior Construction
C20 - Stairs
C30 - Interior Finishes
D10 - Conveying
D20 - Plumbing Systems
D30 - HVAC Systems
D40 - Fire Protection Systems
D50 - Electrical Systems
F10 - Special Construction
F20 - Selective Demolition
General Conditions
Other Direct Cost
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
4) Maximum Allowable Construction Cost
MACC Sub TOTAL | 0 |  | 0
| NA |  | NA | per 0
5a) GCCM Risk Contingency
GCCM Risk Contingency
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
5b) GCCM Costs
GCCM Fee
Bid General Conditions
GCCM Preconstruction Services
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
6) Total Cost of Construction (TCC)
TCC Sub TOTAL | 0 |  | 0
| NA |  | NA | per 0
7) Owner Construction Contingency
Allowance for Change Orders | 0
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
8) Non-Taxable Items
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
9) Sales Tax
Sub TOTAL | 0 |  | 0
CONSTRUCTION CONTRACTS TOTAL | 0 |  | 0
Green cells must be filled in by user

## D. Equipment
Cost Estimate Details
Equipment
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
1) Equipment
E10 - Equipment
E20 - Furnishings
F10 - Special Construction
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
2) Non Taxable Items
Other
Insert Row Here
Sub TOTAL | 0 | 1.2222 | 0
3) Sales Tax
Sub TOTAL | 0 |  | 0
EQUIPMENT TOTAL | 0 |  | 0
Green cells must be filled in by user

## E. Artwork
Cost Estimate Details
Artwork
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
1) Artwork
Project Artwork | 0 |  |  | 0.5% of total project cost for new construction
Higher Ed Artwork | 0 |  |  | 0.5% of total project cost for new and renewal construction
Other
Insert Row Here
ARTWORK TOTAL | 0 | NA | 0
Green cells must be filled in by user

## F. Project Management
Cost Estimate Details
Project Management
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
1) Agency Project Management
Agency Project Management | 0
Additional Services
Other
Insert Row Here
Subtotal of Other | 0
PROJECT MANAGEMENT TOTAL | 0 | 1.2222 | 0
Green cells must be filled in by user

## G. Other Costs
Cost Estimate Details
Other Costs
Item | Base Amount | Escalation Factor | Escalated Cost | Notes
Mitigation Costs
Hazardous Material Remediation/Removal
Historic and Archeological Mitigation
Other
Insert Row Here
OTHER COSTS TOTAL | 0 | 1.2033 | 0
Green cells must be filled in by user

## H. Additional Notes
C-100 (2026)
Additional Notes
Tab A. Acquisition
Insert Row Here
Tab B. Consultant Services
Insert Row Here
Tab C. Construction Contracts
Insert Row Here
Tab D. Equipment
Insert Row Here
Tab E. Artwork
Insert Row Here
Tab F. Project Management
Insert Row Here
Tab G. Other Costs
Insert Row Here

## Audit (hidden)
Named Ranges
| Range Name | Location | Value
| ACQ_TOTAL | ='A. Acquisition'!$C$12 | 0
| ACQ_TOTAL_ESC | ='A. Acquisition'!$F$12 | 0
| TotalMinusPM | =ACQ_TOTAL+CONSUL_TOTAL+MACC+CONT+OTHER_TOTAL
| PREDESIGN_TOTAL | ='B. Consultant Services'!$C$11 | 0
| CONST_DOCS | ='B. Consultant Services'!$C$20 | 0
| OTHER_SVCS_TOTAL | ='B. Consultant Services'!$C$29 | 0
| EX_SVCS_TOTAL | ='B. Consultant Services'!$C$52 | 0
| DES_CONT_TOTAL | ='B. Consultant Services'!$C$58 | 0
| CONSUL_TOTAL | ='B. Consultant Services'!$C$60 | 0
| PREDESIGN_TOTAL_ESC | ='B. Consultant Services'!$F$11 | 0
| CONST_DOCS_ESC | ='B. Consultant Services'!$F$20 | 0
| OTHER_SVCS_TOTAL_ESC | ='B. Consultant Services'!$F$29 | 0
| EX_SVCS_TOTAL_ESC | ='B. Consultant Services'!$F$52 | 0
| DES_CONT_TOTAL_ESC | ='B. Consultant Services'!$F$58 | 0
| CONSUL_TOTAL_ESC | ='B. Consultant Services'!$F$60 | 0
| SITE_TOTAL | ='C. Construction Contracts'!$C$13 | 0
| RELATED_COSTS_TOTAL | ='C. Construction Contracts'!$C$22 | 0
| FACILITY_TOTAL | ='C. Construction Contracts'!$C$42 | 0
| MACC | ='C. Construction Contracts'!$C$55 | 0
| GCCM_RISK | ='C. Construction Contracts'!$C$64 | 0
| GCCM_DB_TOTAL | ='C. Construction Contracts'!$C$72 | 0
| CONT | ='C. Construction Contracts'!$C$86 | 0
| SALES_TAX | ='C. Construction Contracts'!$C$94 | 0
| CONST_TOTAL | ='C. Construction Contracts'!$C$96 | 0
| SITE_TOTAL_ESC | ='C. Construction Contracts'!$F$13 | 0
| RELATED_COSTS_TOTAL_ESC | ='C. Construction Contracts'!$F$22 | 0
| FACILITY_TOTAL_ESC | ='C. Construction Contracts'!$F$42 | 0
| MACC_ESC | ='C. Construction Contracts'!$F$55 | 0
| GCCM_RISK_ESC | ='C. Construction Contracts'!$F$64 | 0
| GCCM_DB_TOTAL_ESC | ='C. Construction Contracts'!$F$72 | 0
| CONT_ESC | ='C. Construction Contracts'!$F$86 | 0
| SALES_TAX_ESC | ='C. Construction Contracts'!$F$94 | 0
| CONST_TOTAL_ESC | ='C. Construction Contracts'!$F$96 | 0
| EQUIP_SUBTOTAL | ='D. Equipment'!$C$10 | 0
| EQUIP_NON_TAX | ='D. Equipment'!$C$15 | 0
| EQUIP_SALES_TAX | ='D. Equipment'!$C$18 | 0
| EQUIP_TOTAL | ='D. Equipment'!$C$20 | 0
| EQUIP_SUBTOTAL_ESC | ='D. Equipment'!$F$10 | 0
| EQUIP_NON_TAX_ESC | ='D. Equipment'!$F$15 | 0
| EQUIP_SALES_TAX_ESC | ='D. Equipment'!$F$18 | 0
| EQUIP_TOTAL_ESC | ='D. Equipment'!$F$20 | 0
| MPD | ='Data Tables'!$H$2 | 2028-08-31 12:00
| MPC | ='Data Tables'!$I$2 | 2031-03-02 12:00
| PMD | ='Data Tables'!$N$1 | 3%
| ART | ='Data Tables'!$N$2 | 0.5%
| Infl | ='Data Tables'!$N$3 | 3.16%
| ContN | ='Data Tables'!$N$4 | 5%
| ContR | ='Data Tables'!$N$5 | 10%
| Rem_Ad | ='Data Tables'!$N$6 | 3%
| PMMinor | ='Data Tables'!$N$7 | 4%
| ART_TOTAL | ='E. Artwork'!$C$9 | 0
| ART_TOTAL_ESC | ='E. Artwork'!$F$9 | 0
| PM_TOTAL | ='F. Project Management'!$C$10 | 0
| AGENCY_PM | ='F. Project Management'!$C$5 | 0
| DES_ADD_SVCS | ='F. Project Management'!$C$6 | 0
| PM_OTHER | ='F. Project Management'!$C$8 | 0
| PM_TOTAL_ESC | ='F. Project Management'!$F$10 | 0
| OTHER_TOTAL | ='G. Other Costs'!$C$10 | 0
| OTHER_TOTAL_ESC | ='G. Other Costs'!$F$10 | 0
| ESC_MidC | =ROUND((1+Infl)^((MPC-Base_Month)/365), 4) | #REF!
| ESC_MidD | =ROUND((1+Infl)^((MPD-Base_Month)/365), 4) | #REF!
| ESC_StartC | =ROUND((1+Infl)^((StartC-Base_Month)/365), 4) | #REF!
| ESC_StartD | =ROUND((1+Infl)^((StartD-Base_Month)/365), 4) | #REF!
| GSF | =Summary!$C$14 | 0
| USF | =Summary!$C$15 | 0
| APW | =Summary!$C$21 | yes
| STR | =Summary!$C$23 | 0.1
| CONT_RATE | =Summary!$C$24 | 0.05
| Base_Month | =Summary!$C$25 | 2024-09-20 11:31
| StartPD | =Summary!$C$29 | 2025-09-01
| StartD | =Summary!$C$30 | 2026-09-01
| StartC | =Summary!$C$31 | 2030-09-01
| Agency | =Summary!$C$4 | 0
| Project_Name | =Summary!$C$5 | 0
| AEFP | =Summary!$F$18 | 0.1651
| Art_Req | =Summary!$F$21 | 0
| HEI | =Summary!$F$22 | 0
| ENDPD | =Summary!$F$29 | 2025-09-01
| EndD | =Summary!$F$30 | 2030-09-01
| EndC | =Summary!$F$31 | 2031-09-01
Formulas:
Value = INDIRECT([Range Name])

## Data Extract (hidden)
Data Extract |  |  |  | 'file:///tmp/in/input.xlsx'#$Data Extract
| Field | Value | Data_type
| Filename | 'file:///tmp/in/input.xlsx'#$Data Extract | text
| Agency | 0 | Text
| Project Name | 0 | text
| OFM Project Number | 0 | Text
| Gross Square Feet | 0 | number
| Usable Square Feet | 0 | number
| Alt Gross | 0 | number
| Alt Gross Unit of Measure | 0 | Text
| Construction Type | Convention facilities | Text
| Remodel | No | Text
| A/E Fee Class | A | Text
| A/E Fee Percentage | 16.51% | percentage
| Projected Life of Asset (Years) | 0 | number
| Procurement Approach | GCCM | Text
| Inflation Rate | 3.16% | percentage
| Sales Tax Rate pct | 10% | percentage
| Location Used for Tax Rate | 0 | Text
| Contingency Rate | 5% | percentage
| Art Requirement Applies | 0% | percentage
| Higher Ed Institution | 0% | percentage
| Base Month (Estimate Date) | 2024-09-20 11:31 | date
| Project Administered By | 0 | Text
| Predesign Start | 2024-09-20 11:31 | date
| Predesign End | 2024-09-20 11:31 | date
| Design Start | 2024-09-20 11:31 | date
| Design End | 2024-09-20 11:31 | date
| Construction Start | 2024-09-20 11:31 | date
| Construction End | 2024-09-20 11:31 | date
| Acquisition Subtotal | 0 | currency
| Acquisition Subtotal Esc | 0 | currency
| Purchase/Lease | 0 | currency
| Appraisal and Closing | 0 | currency
| Right of Way | 0 | currency
| Demolition | 0 | currency
| Pre-Site Development | 0 | currency
| Acquisition Other | 0 | currency
| Predesign Services | 0 | currency
| Predesign Services Esc | 0 | currency
| Programming/Site Analysis | 0 | currency
| Environmental Analysis | 0 | currency
| Predesign Study | 0 | currency
| Predesign Other | 0 | currency
| Design Phase Services | 0 | currency
| Design Phase Services Esc | 0 | currency
| A/E Basic Design Services | 0 | currency
| A/E Basic Design Services Other | 0 | currency
| Extra Services | 0 | currency
| Extra Services Esc | 0 | currency
| Civil Design (Above Basic Svcs) | 0 | currency
| Geotechnical Investigation | 0 | currency
| Commissioning | 0 | currency
| Site Survey | 0 | currency
| Testing | 0 | currency
| LEED Services | 0 | currency
| Voice/Data Consultant | 0 | currency
| Value Engineering | 0 | currency
| Constructability Review | 0 | currency
| Environmental Mitigation (EIS) | 0 | currency
| Landscape Consultant | 0 | currency
| Extra Services Other | 0 | currency
| Other Services | 0 | currency
| Other Services Esc | 0 | currency
| Bid/Construction/Closeout | 0 | currency
| HVAC Balancing | 0 | currency
| Staffing | 0 | currency
| Other Services Other | 0 | currency
| Design Services Contingency | 0 | currency
| Design Services Contingency Esc | 0 | currency
| Design Services Contingency Det | 0 | currency
| Design Services Contingency Other | 0 | currency
| Consultant Services Subtotal | 0 | currency
| Consultant Services Subtotal Esc | 0 | currency
| Site Work | 0 | currency
| Site Work Esc | 0 | currency
| G10 - Site Preparation | 0 | currency
| G20 - Site Improvements | 0 | currency
| G30 - Site Mechanical Utilities | 0 | currency
| G40 - Site Electrical Utilities | 0 | currency
| G60 - Other Site Construction | 0 | currency
| Site work Other | 0 | currency
| Related Project Costs | 0 | currency
| Related Project Costs Esc | 0 | currency
| Offsite Improvements | 0 | currency
| City Utilities Relocation | 0 | currency
| Parking Mitigation | 0 | currency
| Stormwater Retention/Detention | 0 | currency
| Related Project Costs Other | 0 | currency
| Facility Construction | 0 | currency
| Facility Construction Esc | 0 | currency
| A10 - Foundations | 0 | currency
| A20 - Basement Construction | 0 | currency
| B10 - Superstructure | 0 | currency
| B20 - Exterior Closure | 0 | currency
| B30 - Roofing | 0 | currency
| C10 - Interior Construction | 0 | currency
| C20 - Stairs | 0 | currency
| C30 - Interior Finishes | 0 | currency
| D10 - Conveying | 0 | currency
| D20 - Plumbing Systems | 0 | currency
| D30 - HVAC Systems | 0 | currency
| D40 - Fire Protection Systems | 0 | currency
| D50 - Electrical Systems | 0 | currency
| F10 - Special Construction | 0 | currency
| F20 - Selective Demolition | 0 | currency
| General Conditions | 0 | currency
| Facility Construction Other | 0 | currency
| MACC | 0 | currency
| MACC Esc | 0 | currency
| GCCM Risk Contingency | 0 | currency
| GCCM Risk Contingency Esc | 0 | currency
| GCCM Risk Contingency Det | 0 | currency
| GCCM Risk Contingency Other | 0 | currency
| GCCM or Design Build Costs | 0 | currency
| GCCM or Design Build Costs Esc | 0 | currency
| GCCM Fee | 0 | currency
| Bid General Conditions | 0 | currency
| GCCM Preconstruction Services | 0 | currency
| GCCM Fee Other | 0 | currency
| Owner Construction Contingency | 0 | currency
| Owner Construction Contingency Esc | 0 | currency
| Allowance for Change Orders | 0 | currency
| Owner Construction Contingency Other | 0 | currency
| Const Non-Taxable Items | 0 | currency
| Const Non-Taxable Items Esc | 0 | currency
| Sales Tax | 0 | currency
| Sales Tax Esc | 0 | currency
| CONSTRUCTION CONTRACTS TOTAL | 0 | currency
| CONSTRUCTION CONTRACTS TOTAL Esc | 0 | currency
| Equipment | 0 | currency
| Equipment Esc | 0 | currency
| E10 - Equipment | 0 | currency
| E20 - Furnishings | 0 | currency
| F10 - Special Construction - Eq | 0 | currency
| Equipment Other | 0 | currency
| Eq Non Taxable Items | 0 | currency
| Eq Non Taxable Items Esc | 0 | currency
| Eq Sales Tax | 0 | currency
| Eq Sales Tax Esc | 0 | currency
| Sub TOTAL | 1.5 | currency
| EQUIPMENT TOTAL | 0 | currency
| EQUIPMENT TOTAL Esc | 0 | currency
| Project Artwork | 0 | currency
| Higher Ed Artwork | 0 | currency
| Artwork Other | 0 | currency
| ARTWORK TOTAL | 0 | currency
| ARTWORK TOTAL Esc | 0 | currency
| PROJECT MANAGEMENT TOTAL | 0 | currency
| PROJECT MANAGEMENT TOTAL Esc | 0 | currency
| Agency Project Administration Subtotal | 0 | currency
| DES Additional Services Subtotal | 0 | currency
| Other Project Admin Costs | 0 | currency
| OTHER COSTS TOTAL | 0 | currency
| OTHER COSTS TOTAL Esc | 0 | currency
| Add Notes - Acq | Tab A. AcquisitionInsert Row Here | long_text
| Add Notes - Cons | Tab B. Consultant ServicesInsert Row Here | long_text
| Add Notes - Const | Tab C. Construction ContractsInsert Row Here | long_text
| Add Notes - Eq | Tab D. EquipmentInsert Row Here | long_text
| Add Notes - Art | Tab E. ArtworkInsert Row Here | long_text
| Add Notes - PM | Tab F. Project ManagementInsert Row Here | long_text
| Add Notes - Other | Tab G. Other CostsInsert Row Here | long_text

## Data Tables (hidden)
Yes/No | Project Administration | Contingency | Month/Year | Predesign Month/Year | Design Month/Year | Construction Month/Year | Mid-Point of Design | Mid-Point of Construction | A/E Schedule | A/E Fee Class Schedule A | Project Mgmt (AE-4%) | PM Discount | 3%
Yes | Agency | 5% | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2016-01-01 | 2028-08-31 12:00 | 2031-03-02 12:00 | A | 16.51% | 0 | Art | 0.5%
No | DES | 10% | 2016-03-02 | 2016-03-02 | 2016-03-02 | 2016-03-02 |  |  | B | 17.75% |  | Inflation Rate | 3.16%
|  |  | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 |  |  | C | 19% |  | Contingency New | 5%
|  |  | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 |  |  | DBB A | 14.4% |  | Contingency Remodel | 10%
|  |  | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 |  |  | DBB C | 13.76% |  | Remodel Add-on | 3%
|  |  | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 |  |  | GCCM A | 16.51% |  | PM Minor | 4%
DBB | 5% | No | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 |  |  | GCCM C | 19% |  | Base Inflation | 3.16%
DB-Criteria | 1% | No | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31
DB-Bridging | 2% | No | 2017-03-03 | 2017-03-03 | 2017-03-03 | 2017-03-03 |  |  | Other Sch. A Projects | A
DB-Progressive | 1% | No | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 |  |  | Art galleries | A
GCCM | 2% | yes | 2017-07-01 | 2017-07-01 | 2017-07-01 | 2017-07-01 |  |  | Auditorium with stage | A
|  |  | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 |  |  | Communications Building | A
|  |  | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 |  |  | Courthouses | A
|  |  | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 |  |  | Detention/correctional facilities - maximum | A
|  |  | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 |  |  | Exposition building | A
|  |  | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 |  |  | Extended care facilities | A
|  |  | 2018-05-01 | 2018-05-01 | 2018-05-01 | 2018-05-01 |  |  | Fish hatcheries | A
|  |  | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 |  |  | Heating and power plants | A
|  |  | 2018-08-31 | 2018-08-31 | 2018-08-31 | 2018-08-31 |  |  | Hospitals | A
|  |  | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 |  |  | Laboratories (Research) | A
|  |  | 2018-12-01 | 2018-12-01 | 2018-12-01 | 2018-12-01 |  |  | Medical office and clinics | A
|  |  | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-01-31 |  |  | Mental Institutions | A
|  |  | 2019-03-03 | 2019-03-03 | 2019-03-03 | 2019-03-03 |  |  | Museums | A
|  |  | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 |  |  | Observatories | A
|  |  | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  | Research Facilities | A
|  |  | 2019-08-31 | 2019-08-31 | 2019-08-31 | 2019-08-31 |  |  | Sewer treatment plants | A
|  |  | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-01 |  |  | Special schools for physically disadvantaged | A
|  |  | 2019-12-01 | 2019-12-01 | 2019-12-01 | 2019-12-01 |  |  | Theaters and similar facilities | A
|  |  | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | Veterinary hospitals | A
|  |  | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-03-02 |  |  | Water treatment plants | A
|  |  | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-01 |  |  | Other Sch. B Projects | B
|  |  | 2020-07-01 | 2020-07-01 | 2020-07-01 | 2020-07-01 |  |  | Apartment | B
|  |  | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 |  |  | Archive building | B
|  |  | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 |  |  | Armories | B
|  |  | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 |  |  | Auditorium without stage | B
|  |  | 2021-01-31 | 2021-01-31 | 2021-01-31 | 2021-01-31 |  |  | College classroom facilities | B
|  |  | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-03 |  |  | Computer rooms | B
|  |  | 2021-05-01 | 2021-05-01 | 2021-05-01 | 2021-05-01 |  |  | Convention facilities | B
|  |  | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 |  |  | Day care facilities | B
|  |  | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-08-31 |  |  | Detention/correctional facilities - min & max | B
|  |  | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 |  |  | Dining halls/institute | B
|  |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 |  |  | Dormitories | B
|  |  | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-01-31 |  |  | Fire and police stations | B
|  |  | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-03 |  |  | Gymnasiums | B
|  |  | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 |  |  | Laundry and cleaning facilities | B
|  |  | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01 |  |  | Libraries | B
|  |  | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-08-31 |  |  | Neighborhood centers and similar recreation facilities | B
|  |  | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 |  |  | Nursing homes | B
|  |  | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 |  |  | Office buildings | B
|  |  | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 |  |  | Recreational building | B
|  |  | 2023-03-03 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  |  | Residence | B
|  |  | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  | Schools (primary and secondary) | B
|  |  | 2023-07-01 | 2023-07-01 | 2023-07-01 | 2023-07-01 |  |  | Science labs (teaching) | B
|  |  | 2023-08-31 | 2023-08-31 | 2023-08-31 | 2023-08-31 |  |  | Stadiums multi-purpose | B
|  |  | 2023-10-01 | 2023-10-01 | 2023-10-01 | 2023-10-01 |  |  | Storage-cold | B
|  |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 |  |  | Transportation terminals | B
|  |  | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 |  |  | Vocational schools | B
|  |  | 2024-03-02 | 2024-03-02 | 2024-03-02 | 2024-03-02 |  |  | Other Sch. C Projects | C
|  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  | Civil Construction | C
|  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 |  |  | Emergency generator facilities | C
|  |  | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 |  |  | Farm structures | C
|  |  | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 |  |  | Greenhouses | C
|  |  | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 |  |  | Guard towers | C
|  |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-01-31 |  |  | Industrial buildings without special facilities | C
|  |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 |  |  | Parking structures and garages | C
|  |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 |  |  | Printing plants | C
|  |  | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 |  |  | Prototype facilities | C
|  |  | 2025-08-31 | 2025-08-31 | 2025-08-31 | 2025-08-31 |  |  | Service garages | C
|  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 |  |  | Shop and maintenance facilities | C
|  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 |  |  | Simple loft-type structures (w/out special equipment) | C
|  |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  |  | Stadium-grandstand type | C
|  |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-03 |  |  | Warehouses | C
|  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01
|  |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01
|  |  | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31
|  |  | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01
|  |  | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01
|  |  | 2027-01-31 | 2027-01-31 | 2027-01-31 | 2027-01-31
|  |  | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-03
|  |  | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01
|  |  | 2027-07-01 | 2027-07-01 | 2027-07-01 | 2027-07-01
|  |  | 2027-08-31 | 2027-08-31 | 2027-08-31 | 2027-08-31
|  |  | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2027-10-01
|  |  | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01
|  |  | 2028-01-31 | 2028-01-31 | 2028-01-31 | 2028-01-31
|  |  | 2028-03-02 | 2028-03-02 | 2028-03-02 | 2028-03-02
|  |  | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01
|  |  | 2028-07-01 | 2028-07-01 | 2028-07-01 | 2028-07-01
|  |  | 2028-08-31 | 2028-08-31 | 2028-08-31 | 2028-08-31
|  |  | 2028-10-01 | 2028-10-01 | 2028-10-01 | 2028-10-01
|  |  | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01
|  |  | 2029-01-31 | 2029-01-31 | 2029-01-31 | 2029-01-31
|  |  | 2029-03-03 | 2029-03-03 | 2029-03-03 | 2029-03-03
|  |  | 2029-05-01 | 2029-05-01 | 2029-05-01 | 2029-05-01
|  |  | 2029-07-01 | 2029-07-01 | 2029-07-01 | 2029-07-01
|  |  | 2029-08-31 | 2029-08-31 | 2029-08-31 | 2029-08-31
|  |  | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01
|  |  | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01
|  |  | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31
|  |  | 2030-03-03 | 2030-03-03 | 2030-03-03 | 2030-03-03
|  |  | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-05-01
|  |  | 2030-07-01 | 2030-07-01 | 2030-07-01 | 2030-07-01
|  |  | 2030-08-31 | 2030-08-31 | 2030-08-31 | 2030-08-31
|  |  | 2030-10-01 | 2030-10-01 | 2030-10-01 | 2030-10-01
|  |  | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-12-01
|  |  | 2031-01-31 | 2031-01-31 | 2031-01-31 | 2031-01-31
|  |  | 2031-03-03 | 2031-03-03 | 2031-03-03 | 2031-03-03
|  |  | 2031-05-01 | 2031-05-01 | 2031-05-01 | 2031-05-01
|  |  | 2031-07-01 | 2031-07-01 | 2031-07-01 | 2031-07-01
|  |  | 2031-08-31 | 2031-08-31 | 2031-08-31 | 2031-08-31
|  |  | 2031-10-01 | 2031-10-01 | 2031-10-01 | 2031-10-01
|  |  | 2031-12-01 | 2031-12-01 | 2031-12-01 | 2031-12-01
|  |  | 2032-01-31 | 2032-01-31 | 2032-01-31 | 2032-01-31
|  |  | 2032-03-02 | 2032-03-02 | 2032-03-02 | 2032-03-02
|  |  | 2032-05-01 | 2032-05-01 | 2032-05-01 | 2032-05-01
|  |  | 2032-07-01 | 2032-07-01 | 2032-07-01 | 2032-07-01
|  |  | 2032-08-31 | 2032-08-31 | 2032-08-31 | 2032-08-31
|  |  | 2032-10-01 | 2032-10-01 | 2032-10-01 | 2032-10-01
|  |  | 2032-12-01 | 2032-12-01 | 2032-12-01 | 2032-12-01
|  |  | 2033-01-31 | 2033-01-31 | 2033-01-31 | 2033-01-31
|  |  | 2033-03-03 | 2033-03-03 | 2033-03-03 | 2033-03-03
|  |  | 2033-05-01 | 2033-05-01 | 2033-05-01 | 2033-05-01
|  |  | 2033-07-01 | 2033-07-01 | 2033-07-01 | 2033-07-01
|  |  | 2033-08-31 | 2033-08-31 | 2033-08-31 | 2033-08-31
|  |  | 2033-10-01 | 2033-10-01 | 2033-10-01 | 2033-10-01
|  |  | 2033-12-01 | 2033-12-01 | 2033-12-01 | 2033-12-01
|  |  | 2034-01-31 | 2034-01-31 | 2034-01-31 | 2034-01-31
|  |  | 2034-03-03 | 2034-03-03 | 2034-03-03 | 2034-03-03
|  |  | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01
|  |  | 2034-07-01 | 2034-07-01 | 2034-07-01 | 2034-07-01
|  |  | 2034-08-31 | 2034-08-31 | 2034-08-31 | 2034-08-31
|  |  | 2034-10-01 | 2034-10-01 | 2034-10-01 | 2034-10-01
|  |  | 2034-12-01 | 2034-12-01 | 2034-12-01 | 2034-12-01
|  |  | 2035-01-31 | 2035-01-31 | 2035-01-31 | 2035-01-31
|  |  | 2035-03-03 | 2035-03-03 | 2035-03-03 | 2035-03-03
|  |  | 2035-05-01 | 2035-05-01 | 2035-05-01 | 2035-05-01
|  |  | 2035-07-01 | 2035-07-01 | 2035-07-01 | 2035-07-01
|  |  | 2035-08-31 | 2035-08-31 | 2035-08-31 | 2035-08-31
|  |  | 2035-10-01 | 2035-10-01 | 2035-10-01 | 2035-10-01
|  |  | 2035-12-01 | 2035-12-01 | 2035-12-01 | 2035-12-01
|  |  | 2036-01-31 | 2036-01-31 | 2036-01-31 | 2036-01-31
|  |  | 2036-03-02 | 2036-03-02 | 2036-03-02 | 2036-03-02
|  |  | 2036-05-01 | 2036-05-01 | 2036-05-01 | 2036-05-01
|  |  | 2036-07-01 | 2036-07-01 | 2036-07-01 | 2036-07-01
|  |  | 2036-08-31 | 2036-08-31 | 2036-08-31 | 2036-08-31
|  |  | 2036-10-01 | 2036-10-01 | 2036-10-01 | 2036-10-01
|  |  | 2036-12-01 | 2036-12-01 | 2036-12-01 | 2036-12-01
|  |  | 2037-01-31 | 2037-01-31 | 2037-01-31 | 2037-01-31
|  |  | 2037-03-03 | 2037-03-03 | 2037-03-03 | 2037-03-03
|  |  | 2037-05-01 | 2037-05-01 | 2037-05-01 | 2037-05-01
|  |  | 2037-07-01 | 2037-07-01 | 2037-07-01 | 2037-07-01
|  |  | 2037-08-31 | 2037-08-31 | 2037-08-31 | 2037-08-31
|  |  | 2037-10-01 | 2037-10-01 | 2037-10-01 | 2037-10-01
|  |  | 2037-12-01 | 2037-12-01 | 2037-12-01 | 2037-12-01
|  |  | 2038-01-31 | 2038-01-31 | 2038-01-31 | 2038-01-31
|  |  | 2038-03-03 | 2038-03-03 | 2038-03-03 | 2038-03-03
|  |  | 2038-05-01 | 2038-05-01 | 2038-05-01 | 2038-05-01
|  |  | 2038-07-01 | 2038-07-01 | 2038-07-01 | 2038-07-01
|  |  | 2038-08-31 | 2038-08-31 | 2038-08-31 | 2038-08-31
|  |  | 2038-10-01 | 2038-10-01 | 2038-10-01 | 2038-10-01
|  |  | 2038-12-01 | 2038-12-01 | 2038-12-01 | 2038-12-01
|  |  | 2039-01-31 | 2039-01-31 | 2039-01-31 | 2039-01-31
|  |  | 2039-03-03 | 2039-03-03 | 2039-03-03 | 2039-03-03
|  |  | 2039-05-01 | 2039-05-01 | 2039-05-01 | 2039-05-01
|  |  | 2039-07-01 | 2039-07-01 | 2039-07-01 | 2039-07-01
|  |  | 2039-08-31 | 2039-08-31 | 2039-08-31 | 2039-08-31
|  |  | 2039-10-01 | 2039-10-01 | 2039-10-01 | 2039-10-01
|  |  | 2039-12-01 | 2039-12-01 | 2039-12-01 | 2039-12-01
|  |  | 2040-01-31 | 2040-01-31 | 2040-01-31 | 2040-01-31
|  |  | 2040-03-02 | 2040-03-02 | 2040-03-02 | 2040-03-02
|  |  | 2040-05-01 | 2040-05-01 | 2040-05-01 | 2040-05-01
|  |  | 2040-07-01 | 2040-07-01 | 2040-07-01 | 2040-07-01
|  |  | 2040-08-31 | 2040-08-31 | 2040-08-31 | 2040-08-31
|  |  | 2040-10-01 | 2040-10-01 | 2040-10-01 | 2040-10-01
|  |  | 2040-12-01 | 2040-12-01 | 2040-12-01 | 2040-12-01
|  |  | 2041-01-31 | 2041-01-31 | 2041-01-31 | 2041-01-31
|  |  | 2041-03-03 | 2041-03-03 | 2041-03-03 | 2041-03-03
|  |  | 2041-05-01 | 2041-05-01 | 2041-05-01 | 2041-05-01
|  |  | 2041-07-01 | 2041-07-01 | 2041-07-01 | 2041-07-01
|  |  | 2041-08-31 | 2041-08-31 | 2041-08-31 | 2041-08-31
|  |  | 2041-10-01 | 2041-10-01 | 2041-10-01 | 2041-10-01
|  |  | 2041-12-01 | 2041-12-01 | 2041-12-01 | 2041-12-01
|  |  | 2042-01-31 | 2042-01-31 | 2042-01-31 | 2042-01-31
|  |  | 2042-03-03 | 2042-03-03 | 2042-03-03 | 2042-03-03
|  |  | 2042-05-01 | 2042-05-01 | 2042-05-01 | 2042-05-01
|  |  | 2042-07-01 | 2042-07-01 | 2042-07-01 | 2042-07-01
|  |  | 2042-08-31 | 2042-08-31 | 2042-08-31 | 2042-08-31
|  |  | 2042-10-01 | 2042-10-01 | 2042-10-01 | 2042-10-01
|  |  | 2042-12-01 | 2042-12-01 | 2042-12-01 | 2042-12-01
|  |  | 2043-01-31 | 2043-01-31 | 2043-01-31 | 2043-01-31
|  |  | 2043-03-03 | 2043-03-03 | 2043-03-03 | 2043-03-03
|  |  | 2043-05-01 | 2043-05-01 | 2043-05-01 | 2043-05-01
|  |  | 2043-07-01 | 2043-07-01 | 2043-07-01 | 2043-07-01
|  |  | 2043-08-31 | 2043-08-31 | 2043-08-31 | 2043-08-31
|  |  | 2043-10-01 | 2043-10-01 | 2043-10-01 | 2043-10-01
|  |  | 2043-12-01 | 2043-12-01 | 2043-12-01 | 2043-12-01
|  |  | 2044-01-31 | 2044-01-31 | 2044-01-31 | 2044-01-31
|  |  | 2044-03-02 | 2044-03-02 | 2044-03-02 | 2044-03-02
|  |  | 2044-05-01 | 2044-05-01 | 2044-05-01 | 2044-05-01
|  |  | 2044-07-01 | 2044-07-01 | 2044-07-01 | 2044-07-01
|  |  | 2044-08-31 | 2044-08-31 | 2044-08-31 | 2044-08-31
|  |  | 2044-10-01 | 2044-10-01 | 2044-10-01 | 2044-10-01
|  |  | 2044-12-01 | 2044-12-01 | 2044-12-01 | 2044-12-01
|  |  | 2045-01-31 | 2045-01-31 | 2045-01-31 | 2045-01-31
|  |  | 2045-03-03 | 2045-03-03 | 2045-03-03 | 2045-03-03
|  |  | 2045-05-01 | 2045-05-01 | 2045-05-01 | 2045-05-01
|  |  | 2045-07-01 | 2045-07-01 | 2045-07-01 | 2045-07-01
|  |  | 2045-08-31 | 2045-08-31 | 2045-08-31 | 2045-08-31
|  |  | 2045-10-01 | 2045-10-01 | 2045-10-01 | 2045-10-01
|  |  | 2045-12-01 | 2045-12-01 | 2045-12-01 | 2045-12-01
|  |  | 2046-01-31 | 2046-01-31 | 2046-01-31 | 2046-01-31
|  |  | 2046-03-03 | 2046-03-03 | 2046-03-03 | 2046-03-03
|  |  | 2046-05-01 | 2046-05-01 | 2046-05-01 | 2046-05-01
|  |  | 2046-07-01 | 2046-07-01 | 2046-07-01 | 2046-07-01
|  |  | 2046-08-31 | 2046-08-31 | 2046-08-31 | 2046-08-31
|  |  | 2046-10-01 | 2046-10-01 | 2046-10-01 | 2046-10-01
|  |  | 2046-12-01 | 2046-12-01 | 2046-12-01 | 2046-12-01
|  |  | 2047-01-31 | 2047-01-31 | 2047-01-31 | 2047-01-31
|  |  | 2047-03-03 | 2047-03-03 | 2047-03-03 | 2047-03-03
|  |  | 2047-05-01 | 2047-05-01 | 2047-05-01 | 2047-05-01
|  |  | 2047-07-01 | 2047-07-01 | 2047-07-01 | 2047-07-01
|  |  | 2047-08-31 | 2047-08-31 | 2047-08-31 | 2047-08-31
|  |  | 2047-10-01 | 2047-10-01 | 2047-10-01 | 2047-10-01
|  |  | 2047-12-01 | 2047-12-01 | 2047-12-01 | 2047-12-01
|  |  | 2048-01-31 | 2048-01-31 | 2048-01-31 | 2048-01-31
|  |  | 2048-03-02 | 2048-03-02 | 2048-03-02 | 2048-03-02
|  |  | 2048-05-01 | 2048-05-01 | 2048-05-01 | 2048-05-01
|  |  | 2048-07-01 | 2048-07-01 | 2048-07-01 | 2048-07-01
|  |  | 2048-08-31 | 2048-08-31 | 2048-08-31 | 2048-08-31
|  |  | 2048-10-01 | 2048-10-01 | 2048-10-01 | 2048-10-01
|  |  | 2048-12-01 | 2048-12-01 | 2048-12-01 | 2048-12-01
|  |  | 2049-01-31 | 2049-01-31 | 2049-01-31 | 2049-01-31
|  |  | 2049-03-03 | 2049-03-03 | 2049-03-03 | 2049-03-03
|  |  | 2049-05-01 | 2049-05-01 | 2049-05-01 | 2049-05-01
|  |  | 2049-07-01 | 2049-07-01 | 2049-07-01 | 2049-07-01
|  |  | 2049-08-31 | 2049-08-31 | 2049-08-31 | 2049-08-31
|  |  | 2049-10-01 | 2049-10-01 | 2049-10-01 | 2049-10-01
|  |  | 2049-12-01 | 2049-12-01 | 2049-12-01 | 2049-12-01
|  |  | 2050-01-31 | 2050-01-31 | 2050-01-31 | 2050-01-31
|  |  | 2050-03-03 | 2050-03-03 | 2050-03-03 | 2050-03-03
|  |  | 2050-05-01 | 2050-05-01 | 2050-05-01 | 2050-05-01
|  |  | 2050-07-01 | 2050-07-01 | 2050-07-01 | 2050-07-01
|  |  | 2050-08-31 | 2050-08-31 | 2050-08-31 | 2050-08-31
|  |  | 2050-10-01 | 2050-10-01 | 2050-10-01 | 2050-10-01
|  |  | 2050-12-01 | 2050-12-01 | 2050-12-01 | 2050-12-01
|  |  | 2051-01-31 | 2051-01-31 | 2051-01-31 | 2051-01-31
|  |  | 2051-03-03 | 2051-03-03 | 2051-03-03 | 2051-03-03
|  |  | 2051-05-01 | 2051-05-01 | 2051-05-01 | 2051-05-01
|  |  | 2051-07-01 | 2051-07-01 | 2051-07-01 | 2051-07-01
|  |  | 2051-08-31 | 2051-08-31 | 2051-08-31 | 2051-08-31
|  |  | 2051-10-01 | 2051-10-01 | 2051-10-01 | 2051-10-01
|  |  | 2051-12-01 | 2051-12-01 | 2051-12-01 | 2051-12-01
Formulas:
Month/Year = DATE(YEAR([Month/Year, row above]),MONTH([Month/Year, row above])+1,DAY(1))
Predesign Month/Year = DATE(YEAR([Predesign Month/Year, row above]),MONTH([Predesign Month/Year, row above])+1,DAY(1))
Design Month/Year = DATE(YEAR([Design Month/Year, row above]),MONTH([Design Month/Year, row above])+1,DAY(1))
Construction Month/Year = DATE(YEAR([Construction Month/Year, row above]),MONTH([Construction Month/Year, row above])+1,DAY(1))

## Transition (hidden)
Date Ranges
| Estimate Date | 2024-09-20 11:31 |  |  | Days | Wkdays
| Predesign | 2025-09-01 | 2025-09-01 |  | 0 | 1
| Design | 2026-09-01 | 2030-09-01 |  | 1461 | 1044
| Construction | 2030-09-01 | 2031-09-01 |  | 365 | 261
Closeout
Unit of Measure
| GSF | 0 |  | GSF
| Alt | 0 |  | 0
| Use | 0 |  | 0
APW
| Method | GCCM
| APW | yes
Check on Prior & current biennium
| Prior Biennia | 0
| Current Biennium | 0
| Next | 0
| Out | 0
|  |  | prior | current | next | out
| Is there predesign | 0 | 0 | 0 | 1
| Is there design | 1 | 0 | 0 | 1
| Is there construction | 1 | 0 | 0 | 0
Validation Flags
| Funding in prior, but no activity |  | 0
| Activity in prior, but no funding |  | 0
| Activity in current but no funding |  | 0
| Activity in next but no funding |  | 0