## Slide 1: The Learning Center
Update on the LMS Upgrade Project
HR Director’s Meeting
September 2, 2020

## Slide 2: Currently
User Acceptance Testing
Preparing the Production environment
  Agency
  Enterprise

## Slide 3: Task Timing
September
1st – First UAT session
15th – Second UAT session
Completed UAT – ask for full production access
Not all the data will be present however you can start with what is there (see October list)

## Slide 4: Task Timing
October
1st – 23rd – Leverage your training strategy
Build Facilities and Locations – Domain/Agency specific
Update users who you have identified needing elevated roles
October 22 @5PM – Nov 1st – NO LMS availability
Build Audiences
Update online course information
Build Workflows
Build Notifications – Domain/Agency specific
Build Reports that are not out-of-the-box
Create Library Topics
Add Instructors
These could be/are checklists you manage behind the scene

## Slide 5: Task Timing
November
2nd – GO-LIVE!!!
17th – Celebrate!
2nd – 13th – Post-production support for 2 weeks (Hypercare)

## Slide 6: Blackout timeline
Please help communicate out the following:
  October 22, 5PM there is no access to the LMS for anyone to do anything.
  November 2, 7AM the new system will be live for everyone.
    If you have an online course in progress, finish it before or start over after go live.
    Instructor led courses happening during this timeframe will be managed/tracked by the LMS Administrator.

## Slide 7: Questions?