## Master Gantt Chart-New
Overview timeline for Technology and Non-technology dependent initiatives
Note: Legend is at the bottom of the sheet
Procurement and technology dependent initiatives timeline
Major Activity | Spring FY18 | FY19 July 1, 2018 - June 30, 2019 | [11 empty] | FY20 July 1, 2019 - June 30, 2020 | [11 empty] | FY 21 July 1, 2020 - June 30, 2021 | [11 empty] | FY 22 July 1, 2021 - June 30, 2022 | [11 empty] | FY 23 July 1, 2022 - June 30, 2023 | [11 empty] | FY 24 July 1, 2023 - June 30, 2024 | [11 empty] | FY 25 July 1, 2024 - June 30, 2025 | [11 empty] | FY 26 July 1, 2025 - June 30, 2026
Program month |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Implementation month | [17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
Fin/Proc ERP & BI Capabilities Definition and Procurement Activity
Initial ERP Software Acquisition
Market research/ERP software demonstrations
Defining business cpabilities/technical specifications
Drafting the CPP documents
Final merge and publish the CPP documents
Time for vendors to develop proposals
Evaluation, demos, orals, and selection
Negotiations and contracting
QA Services for entire program
Network infrastructure for initial functionality
Technical infrastructure for initial functionality
ERP infrastructure for initial functionality | bar: FY20 July 1, 2019 - June 30, 2020 Apr 6
Expanded ERP software acquisition | bar: FY 23 July 1, 2022 - June 30, 2023 Jan 39
Technical infrastructure for expanded functionality
Specialized consulting services acquisition |  | as needed/if needed | [11 empty] | as needed/if needed |  |  |  | FY 21 July 1, 2020 - June 30, 2021 Jul 9: as needed/if needed; FY 22 July 1, 2021 - June 30, 2022 Jul 21: as needed/if needed; FY 23 July 1, 2022 - June 30, 2023 Jul 33: as needed/if needed
Fin-Proc ERP & BI Implementation
Design/Configure/Test/Deploy Initial/Full Deployment Release | bar: FY20 July 1, 2019 - June 30, 2020 Nov 1 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Initial/Full Deployment Release: initiate and confirm | bar: FY20 July 1, 2019 - June 30, 2020 Nov 1 to FY20 July 1, 2019 - June 30, 2020 Jan 3
Initial/Full Deployment Release: configure, adopt, adapt | bar: FY20 July 1, 2019 - June 30, 2020 Feb 4 to FY 22 July 1, 2021 - June 30, 2022 Mar 29
Initial/Full Deployment Release: test | bar: FY 21 July 1, 2020 - June 30, 2021 Aug 10 to FY 22 July 1, 2021 - June 30, 2022 May 31
Initial Release/Wave 1 : deploy and go-live | bar: FY 21 July 1, 2020 - June 30, 2021 Feb 16 to FY 22 July 1, 2021 - June 30, 2022 Jul 21
Post implementation operations and maintenance
Full Deployment Release/Wave 2: deploy and go-live | bar: FY 22 July 1, 2021 - June 30, 2022 May 31 to FY 23 July 1, 2022 - June 30, 2023 Jul 33
Post implementation operations and maintenance
Design/Configure/Test/Deploy Expanded Functionality Release | bar: FY 23 July 1, 2022 - June 30, 2023 Jul 33 to FY 23 July 1, 2022 - June 30, 2023 Jun 44
Expanded Release/Wave 3 agencies: initiate and confirm | bar: FY 23 July 1, 2022 - June 30, 2023 Jul 33 to FY 23 July 1, 2022 - June 30, 2023 Aug 34
Expanded Release/Wave 3 agencies: configure, adopt, adapt | bar: FY 23 July 1, 2022 - June 30, 2023 Sep 35 to FY 23 July 1, 2022 - June 30, 2023 Feb 40
Expanded Release/Wave 3 agencies: test | bar: FY 23 July 1, 2022 - June 30, 2023 Feb 40 to FY 23 July 1, 2022 - June 30, 2023 Apr 42
Expanded Release/Wave 3: deploy and go-live | bar: FY 23 July 1, 2022 - June 30, 2023 May 43 to FY 24 July 1, 2023 - June 30, 2024 Jul 45
Post implementation operations and maintenance
Design/Configure/Test/Deploy BI for Fin/Proc | bar: FY20 July 1, 2019 - June 30, 2020 Nov 1 to FY 24 July 1, 2023 - June 30, 2024 Jun 56
Budget and HR/Payroll ERP & BI Capabilities Definition and Procurement Activity
Software Acquisition
Market research/ERP software demonstrations
Defining business capabilities/technical specifications
Drafting the CPP documents
Expose draft CPP for review and comment
Time for vendors to develop proposals
Evaluation, demos, orals, and selection
Negotiations and contracting | bar: FY 24 July 1, 2023 - June 30, 2024 Jun 56
Technical Infrastructure (if needed)
Budget & BI Implementation
Design/Configure/Test/Deploy | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 26 July 1, 2025 - June 30, 2026 Dec 74
Full release all agencies: initiate and confirm | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 25 July 1, 2024 - June 30, 2025 Sep 59
Full release all agencies: configure, adopt, adapt | bar: FY 25 July 1, 2024 - June 30, 2025 Oct 60 to FY 25 July 1, 2024 - June 30, 2025 Apr 66
Full release all agencies: test | bar: FY 25 July 1, 2024 - June 30, 2025 May 67 to FY 26 July 1, 2025 - June 30, 2026 Nov 73
Full release all agencies: deploy and go-live | bar: FY 26 July 1, 2025 - June 30, 2026 Nov 73 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
Post implementation operations and maintenance
Design/Configure/Test/Deploy BI for Budget | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
HR/Payroll & BI implementation
Design/Configure/Test/Deploy | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 26 July 1, 2025 - June 30, 2026 Dec 74
Full release all agencies: initiate and confirm | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 25 July 1, 2024 - June 30, 2025 Sep 59
Full release all agencies: configure, adopt, adapt | bar: FY 25 July 1, 2024 - June 30, 2025 Oct 60 to FY 25 July 1, 2024 - June 30, 2025 Apr 66
Full release all agencies: test | bar: FY 25 July 1, 2024 - June 30, 2025 May 67 to FY 26 July 1, 2025 - June 30, 2026 Nov 73
Full release all agencies: deploy and go-live | bar: FY 26 July 1, 2025 - June 30, 2026 Nov 73 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
Post implementation operations and maintenance
Design/Configure/Test/Deploy BI for HR/Payroll | bar: FY 25 July 1, 2024 - June 30, 2025 Jul 57 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
Program management and non-technology dependent initiatives timeline
Major Activity | Spring FY18 | FY19 July 1, 2018 - June 30, 2019 | [11 empty] | FY20 July 1, 2019 - June 30, 2020 |  |  |  | FY 21 July 1, 2020 - June 30, 2021 Jul 9: FY 21 July 1, 2020 - June 30, 2021; FY 22 July 1, 2021 - June 30, 2022 Jul 21: FY 22 July 1, 2021 - June 30, 2022; FY 23 July 1, 2022 - June 30, 2023 Jul 33: FY 23 July 1, 2022 - June 30, 2023; FY 24 July 1, 2023 - June 30, 2024 Jul 45: FY 24 July 1, 2023 - June 30, 2024; FY 25 July 1, 2024 - June 30, 2025 Jul 57: FY 25 July 1, 2024 - June 30, 2025; FY 26 July 1, 2025 - June 30, 2026 Jul 69: FY 26 July 1, 2025 - June 30, 2026
Program month |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Implementation month | [17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
Executive program management and Quality Assurance.
Assess Procurement Organizational Strategy
Assess Finance Organizational Strategy and Readiness
Assess the Opportunities to Simplify and Improve Budget Processes | bar: FY20 July 1, 2019 - June 30, 2020 Nov 1 to FY20 July 1, 2019 - June 30, 2020 Dec 2
Review HR/Payroll Statute and Business Processes | bar: FY20 July 1, 2019 - June 30, 2020 Nov 1 to FY20 July 1, 2019 - June 30, 2020 Jun 8
Assess the Feasibility of Creating a Center of Excellence for HR/Payroll | bar: FY 21 July 1, 2020 - June 30, 2021 Jul 9 to FY 21 July 1, 2020 - June 30, 2021 Jun 20
Assess the Ability to Intercept/Offset Delinquent Debt | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Define and Implement Procurement Key Performance Indicators | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Finance Readiness Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Grants Management Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Enterprise Solicitation Processes Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Supplier Relationship Management Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Non-Tax Revenue Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Launch Indirect Cost Allocation Review Workgroup | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Jun 32
Interface and Conversion Development timeline
Major Activity | Spring FY18 | FY19 July 1, 2018 - June 30, 2019 | [11 empty] | FY20 July 1, 2019 - June 30, 2020 |  |  |  | FY 21 July 1, 2020 - June 30, 2021 Jul 9: FY 21 July 1, 2020 - June 30, 2021; FY 22 July 1, 2021 - June 30, 2022 Jul 21: FY 22 July 1, 2021 - June 30, 2022; FY 23 July 1, 2022 - June 30, 2023 Jul 33: FY 23 July 1, 2022 - June 30, 2023; FY 24 July 1, 2023 - June 30, 2024 Jul 45: FY 24 July 1, 2023 - June 30, 2024; FY 25 July 1, 2024 - June 30, 2025 Jul 57: FY 25 July 1, 2024 - June 30, 2025; FY 26 July 1, 2025 - June 30, 2026 Jul 69: FY 26 July 1, 2025 - June 30, 2026
Program month |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Implementation month | [17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
Interface and Conversion Development for Finance and Procurement
Initial Release/Wave 1 agencies: design | bar: FY20 July 1, 2019 - June 30, 2020 Feb 4 to FY20 July 1, 2019 - June 30, 2020 Apr 6
Initial Release/Wave 1 agencies: build | bar: FY20 July 1, 2019 - June 30, 2020 May 7 to FY 21 July 1, 2020 - June 30, 2021 Oct 12
Initial Release/Wave 1 agencies: test | bar: FY 21 July 1, 2020 - June 30, 2021 Nov 13 to FY 21 July 1, 2020 - June 30, 2021 Apr 18
Initial Release/Wave 1 agencies: deploy and go-live | bar: FY 21 July 1, 2020 - June 30, 2021 May 19 to FY 22 July 1, 2021 - June 30, 2022 Jul 21
Full Deployment/Wave 2 agencies: design | bar: FY 22 July 1, 2021 - June 30, 2022 Jul 21 to FY 22 July 1, 2021 - June 30, 2022 Sep 23
Full Deployment/Wave 2 agencies: build | bar: FY 22 July 1, 2021 - June 30, 2022 Oct 24 to FY 22 July 1, 2021 - June 30, 2022 Jan 27
Full Deployment/Wave 2 agencies: test | bar: FY 22 July 1, 2021 - June 30, 2022 Feb 28 to FY 22 July 1, 2021 - June 30, 2022 May 31
Full Deployment/Wave 2 agencies: deploy and go-live | bar: FY 22 July 1, 2021 - June 30, 2022 Jun 32 to FY 23 July 1, 2022 - June 30, 2023 Jul 33
Expanded Release/Wave 3 agencies: design | bar: FY 23 July 1, 2022 - June 30, 2023 Jul 33 to FY 23 July 1, 2022 - June 30, 2023 Sep 35
Expanded Release/Wave 3 agencies: build | bar: FY 23 July 1, 2022 - June 30, 2023 Oct 36 to FY 23 July 1, 2022 - June 30, 2023 Jan 39
Expanded Release/Wave 3 agencies: test | bar: FY 23 July 1, 2022 - June 30, 2023 Feb 40 to FY 23 July 1, 2022 - June 30, 2023 Apr 42
Expanded Release/Wave 3 agencies: deploy and go-live | bar: FY 23 July 1, 2022 - June 30, 2023 May 43 to FY 24 July 1, 2023 - June 30, 2024 Jul 45
Interface and Conversion Development for Budget
Full release all agencies: design | bar: FY 25 July 1, 2024 - June 30, 2025 Oct 60 to FY 25 July 1, 2024 - June 30, 2025 Dec 62
Full release all agencies: build | bar: FY 25 July 1, 2024 - June 30, 2025 Jan 63 to FY 25 July 1, 2024 - June 30, 2025 May 67
Full release all agencies: test | bar: FY 25 July 1, 2024 - June 30, 2025 Jun 68 to FY 26 July 1, 2025 - June 30, 2026 Oct 72
Full release all agencies: deploy and go-live | bar: FY 26 July 1, 2025 - June 30, 2026 Nov 73 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
Interface and Conversion Development for HR/Payroll
Full release all agencies: design | bar: FY 25 July 1, 2024 - June 30, 2025 Oct 60 to FY 25 July 1, 2024 - June 30, 2025 Dec 62
Full release all agencies: build | bar: FY 25 July 1, 2024 - June 30, 2025 Jan 63 to FY 25 July 1, 2024 - June 30, 2025 May 67
Full release all agencies: test | bar: FY 25 July 1, 2024 - June 30, 2025 Jun 68 to FY 26 July 1, 2025 - June 30, 2026 Oct 72
Full release all agencies: deploy and go-live | bar: FY 26 July 1, 2025 - June 30, 2026 Nov 73 to FY 26 July 1, 2025 - June 30, 2026 Jan 75
LEGENDS
ERP Procurement Activity
Go-Live Month
ERP Implementation overall timelines
Implementation - waves/ Non-tech initiatives
6 months support
6 months support
6 months support
6 months support
12 months for CAFR)
6 months support

## New Summary Slide
FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26
Implement Finance & Procurement
Implement Budget
Implement Business Intelligence
Procure Fin/Proc/BI
Procure Budget & HR/Payroll
Implement HR/Payroll
Procurement
Implement
Go-Live
Implement Finance & Procurement
Implement Budget
Implement Business Intelligence
Procure Fin/Proc/BI
Procure Budget & HR/Payroll
Implement HR/Payroll
Procurement
Implement
Go-Live

## Non-Tech Summary Gantt
Program management and non-technology dependent initiatives timeline
Major Activity | Spring FY18 | FY19 July 1, 2018 - June 30, 2019 | FY20 July 1, 2019 - June 30, 2020 | FY 21 July 1, 2020 - June 30, 2021 | FY 22 July 1, 2021 - June 30, 2022 | FY 23 July 1, 2022 - June 30, 2023 | FY 24 July 1, 2023 - June 30, 2024 | FY 25 July 1, 2024 - June 30, 2025 | FY 26 July 1, 2025 - June 30, 2026
Executive Program Management and Quality Assurance.
Assess Procurement Organizational Strategy
Assess Finance Organizational Strategy and Readiness
Assess Opportunities to Simplify and Improve Budget Processes
Review HR/Payroll Statute and Business Processes
Assess the Feasibility of Creating a Center of Excellence for HR/Payroll
Assess the Ability to Intercept/Offset Delinquent Debt
Define and Implement Procurement Key Performance Indicators
Launch Finance Readiness Workgroup
Launch Grants Management Workgroup
Launch Enterprise Solicitation Processes Workgroup
Launch Supplier Relationship Management Workgroup
Launch Non-Tax Revenue Workgroup
Launch Indirect Cost Allocation Review Workgroup
LEGENDS
Non-tech initiatives