## Non-Tech Summary Gantt
Program management and non-technology dependent initiatives timeline
Major Activity | Spring FY18 | FY19 July 1, 2018 - June 30, 2019 | FY20 July 1, 2019 - June 30, 2020 | FY 21 July 1, 2020 - June 30, 2021 | FY 22 July 1, 2021 - June 30, 2022 | FY 23 July 1, 2022 - June 30, 2023 | FY 24 July 1, 2023 - June 30, 2024 | FY 25 July 1, 2024 - June 30, 2025 | FY 26 July 1, 2025 - June 30, 2026
Executive Program Management and Quality Assurance.
Assess Procurement Organizational Strategy
Assess Finance Organizational Strategy and Readiness
Assess Opportunities to Simplify and Improve Budget Processes
Review HR/Payroll Statutes and Business Processes
Assess the Feasibility of Creating a Center of Excellence for HR/Payroll
Assess the Ability to Intercept/Offset Delinquent Debt
Define and Implement Procurement Key Performance Indicators
Launch Finance Readiness Workgroup
Launch Grants Management Workgroup
Launch Enterprise Solicitation Processes Workgroup
Launch Supplier Relationship Management Workgroup
Launch Non-Tax Revenue Workgroup
Launch Indirect Cost Allocation Review Workgroup
LEGENDS
Non-tech initiatives