## FY20 FY21 Biennium Guidance
Detail for Wave 1 agencies is in beige colored region. Wave 2 agencies in green.
[6 empty] | FY20 | [11 empty] | FY21 | [12 empty] | FY22 | [12 empty] | FY23 | [11 empty] | FY24 | [11 empty] | FY25 | [11 empty] | FY25
Wave | Activity Area | Activity Details | Activity Description | One Washington role | Agency role | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J |  | J | A | S | O | N | D | J | F | M | A | M | J |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Initial (10 agencies) | Configuration | Design | The processes, workflow, business and technical capabilities applied to the software solution. | 1 - Conduct and coordinate ERP design configuration workshops for Finance and Procurement, these sessions will be facilitated by functional SMEs 2 - Compile and document the configurations | 1 - Agencies will provide Finance and Procurement SMEs for participation in workshops and sessions, 2 - SMEs will review and signoff on the configuration documents | [24 empty] | Initial Release | [12 empty] | Full Deployment
|  | Build |  | 1 - Work with vendor to configure the product based on finalized designs 2 - Conduct unit test of configurations | 1 - Minimal participation is expected from agencies during the actual configuration of the solution, One Washington will be working closely with the software vendor to implement the design configurations 2 - Agency may be asked to provide sample production like data that will be used for unit/integration testing
| Integration | Design | Process of bringing together components of upstream and downstream systems into the solution. | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized interfaces 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement integration functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for integrations | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized interfaces with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build |  | 1 - Work with the vendor to build integrations based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for integrations | 1 - Agencies will make modifications to their systems for new integrations 2 - Agencies will conduct their own unit test for their systems, and any downstream systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
| Master Data Management | Governance | Methods used to define, centralize and manage the critical data of an organization with data integrity. | 1 - Oversee the implementation of the master data strategy 2 - Work closely with Data Governance advisory group to define master data 3 - The program working through the Data Governance groups will validate master data is implemented as designed and managed effectively through the governance plan | 1 - Where applicable, agencies will participate in master data discussions and decisions, these will be mainly facilitated by the data governance advisory groups 2 - Agencies will be apprised of updates (through the communication plan) and validate the their agencies follows the guidance of the master data plan/advisory groups
| Data Conversions | Design | Transformation (or translation) of data from one format to another. Ensuring data integrity for consumption. | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized conversions 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement conversion functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for conversions | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized conversions with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build |  | 1 - Work with the vendor to build conversion mapping based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for conversions | 1 - Agencies will cleanse the data that will be converted 2 - Agencies will extract the data from legacy systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
| Reports | Design | Out-of-box generated reports. | 1 - Conduct design workshops and sessions to configure ERP reports 2 - Document and finalize canned and custom report designs | 1 - Agencies will participate in workshops or sessions to define the 'canned' and custom ERP reports 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the vendor to configure canned and build custom reports | 1 - Minimal participation is expected from agencies
| Security | Design | Agency role administration and security capabilities to connect to a SaaS solution. | 1 - Oversee the implementation of the security plan 2 - Document a security plan that abides by the security policies of the state 3 - Obtain approvals from applicable agencies on the security plan | 1 - Applicable agencies will work closely with the program to define and implement the security plan 2 - Applicable agencies will provide their expertise in state policies and procedures 3 - Applicable agencies will review and provide signoff on security plans
|  | Build |  | 1 - One Washington will work with the vendor to configure the ERP and BI solution as defined in the security plan | 1 - Minimal participation is expected from agencies
| Business Intelligence | Design | Data analytics and tool provided by selected solution. | 1 - Conduct design workshops and sessions to configure BI dashboards, reports and tools 2 - Document and finalize canned and custom BI reports, dashboards, and tools designs | 1 - Agencies will participate in workshops or sessions to define BI reports, dashboards and tools 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the BI solution vendor to configure and build BI reports, tools and dashboards | 1 - Minimal participation is expected from agencies
| OCM - Communications | Communications | What are the methods and approaches the agency will develop to manage, communicate and enable impacted agency stakeholders to successfully transform business processes and adopt a modern enterprise system for Finance, Procurement, HR/Payroll, Budget and Business Intelligence? Considerations: Communications, training, engagement activities, and readiness | 1 - One Washington will develop and implement a comprehensive communications plan that will keep agencies and stakeholders apprised of key program information (for Finance and Procurement) 2 - Communications plan will send clear 'call to action' directions in a timely manner | 1 - Agencies will keep updated of overall One Washington status via their change agent(s) 2 - When requested, agencies will respond to request from the program in a timely manner
| OCM - Training | Training |  | 1 - One Washington will develop and implement a comprehensive training plan for finance, procurement and BI 2 - Training plan will define the training curriculum and schedule | 1 - Minimal participation from agencies is expected 2 - Agencies will plan/coordinate with the applicable staff to attend training
| OCM - Engagement & Readiness | Engagement |  | 1 - OCM will develop and implement an agency and stakeholder engagement plan | 1 - Agencies will review the engagement plan, align to its actions and objectives, and ensure key agency staff align to overall program objectives
|  | Readiness |  | 1 - OCM will develop a comprehensive readiness checklist 2 - OCM will review the readiness checklist with agencies | 1 - Agencies will participate in all readiness planning activities 2 - Agencies will review and implement the applicable tasks as defined in the readiness checklist
| Testing | Unit Test | Source code, modules with controlled data and procedures testing. | 1 - Develop a Unit test plan to validate configurations, interfaces and conversions 2 - Perform unit test and validate configurations, interfaces and conversions (confirm data mappings and integrity of items developed) | 1 - Agencies will unit test their line of business and any downstream systems to validate the modifications made are correct
|  | System Test | Conducted on a complete, integrated system to evaluate compliance. | 1 - Develop a System test to validate configurations, interfaces and conversions 2 - Conduct system test using mock data on interfaces, conversions, crosswalks and data maps 3 - Resolve issues and defects | 1 - Agencies will provide input on system test scripts 2 - Agencies will provide mock data 3 - Agencies will be part of the defect remediation process 4 - Agencies will system test their line of business and any downstream systems to validate the modifications made are correct
|  | Integration Test | Overall testing of the complete system including sub-systems components and integration layer. | 1 - Create a Integration test plan that will validate the interfaces and data conversions 2 - Coordinate all integration testing activities including test script development, execution, mock data coordination and defect remediation | 1 - Agencies will review the test plan and test scripts 2 - Agencies will be involved in interface and data conversion testing, the effort involved will be determined by the number of systems (defined in the One Washington System Impact Summary), major activities include: • Agencies will be responsible for creating their own data crosswalks, for interfaces and conversions, that will be loaded to the integration layer • Agencies will be responsible for extracting the data from their legacy system(s). • Agencies will provide One Washington with mock data for testing • Agencies will provide One Washington with production like data for mock conversions, and validate the results of the mock conversions • Agencies will validate that the mock conversion data is correct • Agencies will resolve any issues that result from the mock conversion validation • Agencies will provide One Washington with the final production data that will be loaded in the production environment • Agencies document and work with One Washington to resolve defects (retesting if required)
|  | Performance Test | Testing of responsiveness and stability within various workloads. | 1 - Plan and execute performance test with simulated interface transaction volume to ensure the online application will be able to handle expected volumes | 1 - Agencies will provide expected volumes of business processes, this information will be added to the performance test plans
|  | User Acceptance (UAT) | Testing to validate solutions / system capabilities to meet business and technical needs. Exposure to the solution prior to formal training and allows users to interact with system and functionality. | 1 - Conduct final user acceptance testing of ERP configurations, interfaces and configurations 2 - Coordinate the resolution of any issues or defects | 1 - Agencies will perform User Acceptance testing of configurations, interfaces and conversions by executing business scenarios - Agencies will develop test scripts based on agency business scenarios - Agencies will execute the test scripts and report findings and issues to the program - Agencies will work with the program to resolve issues or defects
|  | Readiness | Overall system and operational readiness. | 1 - Create readiness plan that will in include final validation before code is deployed to production | 1 - Agencies will perform final readiness testing to validate code is ready for production deployment 2 - Along with the program readiness activities, agencies will be responsible for creating their own internal deployment and communications plans
Full (34 agencies) | Configuration | Design | The processes, workflow, business and technical capabilities applied to the software solution. | 1 - Conduct and coordinate ERP design configuration workshops for Finance and Procurement, these sessions will be facilitated by functional SMEs 2 - Compile and document the configurations | 1 - Agencies will provide Finance and Procurement SMEs for participation in workshops and sessions, 2 - SMEs will review and signoff on the configuration documents | [24 empty] | Initial Release
|  | Build |  | 1 - Work with vendor to configure the product based on finalized designs 2 - Conduct unit test of configurations | 1 - Minimal participation is expected from agencies during the actual configuration of the solution, One Washington will be working closely with the software vendor to implement the design configurations 2 - Agency may be asked to provide sample production like data that will be used for unit/integration testing
| Integration | Design | Process of bringing together components of upstream and downstream systems into the solution. | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized interfaces 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement integration functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for integrations | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized interfaces with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build |  | 1 - Work with the vendor to build integrations based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for integrations | 1 - Agencies will make modifications to their systems for new integrations 2 - Agencies will conduct their own unit test for their systems, and any downstream systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
| Master Data Management | Governance | Methods used to define, centralize and manage the critical data of an organization with data integrity. | 1 - Oversee the implementation of the master data strategy 2 - Work closely with Data Governance advisory group to define master data 3 - The program working through the Data Governance groups will validate master data is implemented as designed and managed effectively through the governance plan | 1 - Where applicable, agencies will participate in master data discussions and decisions, these will be mainly facilitated by the data governance advisory groups 2 - Agencies will be apprised of updates (through the communication plan) and validate the their agencies follows the guidance of the master data plan/advisory groups
| Data Conversions | Design | Transformation (or translation) of data from one format to another. Ensuring data integrity for consumption. | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized conversions 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement conversion functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for conversions | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized conversions with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build |  | 1 - Work with the vendor to build conversion mapping based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for conversions | 1 - Agencies will cleanse the data that will be converted 2 - Agencies will extract the data from legacy systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
| Reports | Design | Out-of-box generated reports. | 1 - Conduct design workshops and sessions to configure ERP reports 2 - Document and finalize canned and custom report designs | 1 - Agencies will participate in workshops or sessions to define the 'canned' and custom ERP reports 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the vendor to configure canned and build custom reports | 1 - Minimal participation is expected from agencies
| Security | Design | Agency role administration and security capabilities to connect to a SaaS solution. | 1 - Oversee the implementation of the security plan 2 - Document a security plan that abides by the security policies of the state 3 - Obtain approvals from applicable agencies on the security plan | 1 - Applicable agencies will work closely with the program to define and implement the security plan 2 - Applicable agencies will provide their expertise in state policies and procedures 3 - Applicable agencies will review and provide signoff on security plans
|  | Build |  | 1 - One Washington will work with the vendor to configure the ERP and BI solution as defined in the security plan | 1 - Minimal participation is expected from agencies
| Business Intelligence | Design | Data analytics and tool provided by selected solution. | 1 - Conduct design workshops and sessions to configure BI dashboards, reports and tools 2 - Document and finalize canned and custom BI reports, dashboards, and tools designs | 1 - Agencies will participate in workshops or sessions to define BI reports, dashboards and tools 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the BI solution vendor to configure and build BI reports, tools and dashboards | 1 - Minimal participation is expected from agencies
| OCM - Communications | Communications | What are the methods and approaches the agency will develop to manage, communicate and enable impacted agency stakeholders to successfully transform business processes and adopt a modern enterprise system for Finance, Procurement, HR/Payroll, Budget and Business Intelligence? Considerations: Communications, training, engagement activities, and readiness | 1 - One Washington will develop and implement a comprehensive communications plan that will keep agencies and stakeholders apprised of key program information (for Finance and Procurement) 2 - Communications plan will send clear 'call to action' directions in a timely manner | 1 - Agencies will keep updated of overall One Washington status via their change agent(s) 2 - When requested, agencies will respond to request from the program in a timely manner
| OCM - Training | Training |  | 1 - One Washington will develop and implement a comprehensive training plan for finance, procurement and BI 2 - Training plan will define the training curriculum and schedule | 1 - Minimal participation from agencies is expected 2 - Agencies will plan/coordinate with the applicable staff to attend training
| OCM - Engagement & Readiness | Engagement |  | 1 - OCM will develop and implement an agency and stakeholder engagement plan | 1 - Agencies will review the engagement plan, align to its actions and objectives, and ensure key agency staff align to overall program objectives
|  | Readiness |  | 1 - OCM will develop a comprehensive readiness checklist 2 - OCM will review the readiness checklist with agencies | 1 - Minimal participation from agencies is expected 2 - Agencies will review and implement the applicable tasks as defined in the readiness checklist
Expanded | Configuration | Design | Source code, modules with controlled data and procedures testing. | 1 - Conduct and coordinate ERP design configuration workshops for Finance and Procurement, these sessions will be facilitated by functional SMEs 2 - Compile and document the configurations | 1 - Agencies will provide Finance and Procurement SMEs for participation in workshops and sessions, 2 - SMEs will review and signoff on the configuration documents
|  | Build | Conducted on a complete, integrated system to evaluate compliance. | 1 - Work with vendor to configure the product based on finalized designs 2 - Conduct unit test of configurations | 1 - Minimal participation is expected from agencies during the actual configuration of the solution, One Washington will be working closely with the software vendor to implement the design configurations 2 - Agency may be asked to provide sample production like data that will be used for unit/integration testing
|  | Validation | Overall testing of the complete system including sub-systems components and integration layer. | 1 - Oversee and coordinate testing (will include integration, end to end and final user acceptance) of the ERP solution to validate configuration aligns to final designs 2 - Conduct system and integration end to end testing 3 - Facilitate user acceptance testing with agencies | 1 - Agencies will support the testing activities defined in the overall test plan 2 - Agency will provide sample production to support this testing phase 3 - Agencies will perform user acceptance testing of the Finance and Procurement modules to confirm the functionality was configured per design
| Integration | Design | Testing of responsiveness and stability within various workloads. | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized interfaces 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement integration functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for integrations | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized interfaces with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build | Testing to validate solutions / system capabilities to meet business and technical needs. Exposure to the solution prior to formal training and allows users to interact with system and functionality. | 1 - Work with the vendor to build integrations based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for integrations | 1 - Agencies will make modifications to their systems for new integrations 2 - Agencies will conduct their own unit test for their systems, and any downstream systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
|  | Validation | Overall system and operational readiness. | 1 - Oversee and coordinate testing (will include integration, end to end and final user acceptance) of the ERP solution to validate integrations align with functional and technical specifications 2 - Conduct system and integration end to end testing 3 - Facilitate user acceptance testing with agencies | 1 - Agencies will support the testing activities defined in the overall test plan 2 - Agency will provide sample production like data to support this testing phase 3 - Agencies will perform user acceptance testing for integrations 4 - Agencies will test downstream systems
| Master Data Management | Governance |  | 1 - Oversee the implementation of the master data strategy 2 - Work closely with Data Governance advisory group to define master data 3 - The program working through the Data Governance groups will validate master data is implemented as designed and managed effectively through the governance plan | 1 - Where applicable, agencies will participate in master data discussions and decisions, these will be mainly facilitated by the data governance advisory groups 2 - Agencies will be apprised of updates (through the communication plan) and validate the their agencies follows the guidance of the master data plan/advisory groups
| Data Conversions | Design |  | 1 - Confirm list of systems to be retired with agencies 2 - Finalize the list of consolidated and standardized conversions 3 - Define development timeline 4 - Review timeline with agencies 5 - Create Finance and Procurement conversion functional and technical designs 6 - Conduct sessions to finalize the functional and technical designs for conversions | 1- Confirm list of systems to be retired with One Washington 2 - Review list of consolidated and standardized conversions with One Washington 3 - Review development timelines with One Washington 4 - Agencies SMEs will participate in the finalization of functional and technical designs and provide sign off
|  | Build |  | 1 - Work with the vendor to build conversion mapping based on the functional and technical specifications 2 - Load agency crosswalks 3 - Conduct unit test for conversions | 1 - Agencies will cleanse the data that will be converted 2 - Agencies will extract the data from legacy systems 3 - Agencies will create data crosswalks 4 - Agencies may be asked to provide sample production like data that will be used during unit test
|  | Validation |  | 1 - Oversee and coordinate testing (will include integration, end to end and final user acceptance) of the ERP solution to validate conversions align with functional and technical specifications 2 - Conduct system and integration end to end testing 3 - Facilitate user acceptance testing with agencies | 1 - Agencies will support the testing activities defined in the overall test plan 2 - Agencies will provide mock conversion files along with data crosswalks to support testing 3 - Agencies will perform user acceptance testing for conversions
| Reports | Design |  | 1 - Conduct design workshops and sessions to configure ERP reports 2 - Document and finalize canned and custom report designs | 1 - Agencies will participate in workshops or sessions to define define the 'canned' and custom ERP reports 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the vendor to configure canned and build custom reports | 1 - Minimal participation is expected from agencies
|  | Validation |  | 1 - One Washington will perform initial validation of canned and custom reports 2 - Coordinate final user acceptance testing of canned and custom reports with agencies | 1 - Agencies may be asked to provide sample production like data to test canned and custom reports 2 - Agencies will perform final user acceptance testing of canned and custom reports
| Security | Design |  | 1 - Oversee the implementation of the security plan 2 - Document a security plan that abides by the security policies of the state 3 - Obtain approvals from applicable agencies on the security plan | 1 - Applicable agencies will work closely with the program to define and implement the security plan 2 - Applicable agencies will provide their expertise in state policies and procedures 3 - Applicable agencies will review and provide signoff on security plans
|  | Build |  | 1 - One Washington will work with the vendor to configure the ERP and BI solution as defined in the security plan | 1 - Minimal participation is expected from agencies
|  | Validation |  | 1 - One Washington will perform initial validation of security configurations, user profiles, etc. | 1 - Agencies may be asked to provide sample production like data or user profiles to validate security configurations in the solution
| Business Intelligence | Design |  | 1 - Conduct design workshops and sessions to configure BI dashboards, reports and tools 2 - Document and finalize canned and custom BI reports, dashboards, and tools designs | 1 - Agencies will participate in workshops or sessions to define BI reports, dashboards and tools 2 - Agencies will review and signoff on final designs
|  | Build |  | 1 - One Washington will work with the BI solution vendor to configure and build BI reports, tools and dashboards | 1 - Minimal participation is expected from agencies
|  | Validation |  | 1 - One Washington will perform initial validation of BI reports, tools and dashboards 2 - Coordinate final user acceptance testing of BI reports, tools and dashboards | 1 - Agencies may be asked to provide sample production like data to test BI reports, tools and dashboards 2 - Agencies will perform final user acceptance testing of BI reports, tools and dashboards
| OCM - Communications | Communications |  | 1 - One Washington will develop and implement a comprehensive communications plan that will keep agencies and stakeholders apprised of key program information (for Finance and Procurement) 2 - Communications plan will send clear 'call to action' directions in a timely manner | 1 - Agencies will keep updated of overall One Washington status via their change agent(s) 2 - When requested, agencies will respond to request from the program in a timely manner
| OCM - Training | Training |  | 1 - One Washington will develop and implement a comprehensive training plan for finance, procurement and BI 2 - Training plan will define the training curriculum and schedule | 1 - Minimal participation from agencies is expected 2 - Agencies will plan/coordinate with the applicable staff to attend training
| OCM - Engagement & Readiness | Engagement |  | 1 - OCM will develop and implement an agency and stakeholder engagement plan | 1 - Agencies will review the engagement plan, align to its actions and objectives, and ensure key agency staff align to overall program objectives
|  | Readiness |  | 1 - OCM will develop a comprehensive readiness checklist 2 - OCM will review the readiness checklist with agencies | 1 - Minimal participation from agencies is expected 2 - Agencies will review and implement the applicable tasks as defined in the readiness checklist
| Testing | Unit Test | Source code, modules with controlled data and procedures testing. | 1 - Develop a Unit test plan to validate configurations, interfaces and conversions 2 - Perform unit test and validate configurations, interfaces and conversions (confirm data mappings and integrity of items developed) | 1 - Agencies will unit test their line of business and any downstream systems to validate the modifications made are correct
|  | System Test | Conducted on a complete, integrated system to evaluate compliance. | 1 - Develop a System test to validate configurations, interfaces and conversions 2 - Conduct system test using mock data on interfaces, conversions, crosswalks and data maps 3 - Resolve issues and defects | 1 - Agencies will provide input on system test scripts 2 - Agencies will provide mock data 3 - Agencies will be part of the defect remediation process
|  | Integration Test | Overall testing of the complete system including sub-systems components and integration layer. | 1 - Create a Integration test plan that will validate the interfaces and data conversions 2 - Coordinate all integration testing activities including test script development, execution, mock data coordination and defect remediation | 1 - Agencies will review the test plan and test scripts 2 - Agencies will be involved in interface and data conversion testing, the effort involved will be determined by the number of systems (defined in the One Washington System Impact Summary), major activities include: • Agencies will be responsible for creating their own data crosswalks, for interfaces and conversions, that will be loaded to the integration layer • Agencies will be responsible for extracting the data from their legacy system(s). • Agencies will provide One Washington with mock data for testing • Agencies will provide One Washington with production like data for mock conversions, and validate the results of the mock conversions • Agencies will validate that the mock conversion data is correct • Agencies will resolve any issues that result from the mock conversion validation • Agencies will provide One Washington with the final production data that will be loaded in the production environment • Agencies document and work with One Washington to resolve defects (retesting if required)
|  | Performance Test | Testing of responsiveness and stability within various workloads. | 1 - Plan and execute performance test with simulated interface transaction volume to ensure the online application will be able to handle expected volumes | 1 - Agencies will provide expected volumes of business processes, this information will be added to the performance test plans
|  | User Acceptance (UAT) | Testing to validate solutions / system capabilities to meet business and technical needs. Exposure to the solution prior to formal training and allows users to interact with system and functionality. | 1 - Conduct final user acceptance testing of ERP configurations, interfaces and configurations 2 - Coordinate the resolution of any issues or defects | 1 - Agencies will perform User Acceptance testing of configurations, interfaces and conversions by executing business scenarios - Agencies will develop test scripts based on agency business scenarios - Agencies will execute the test scripts and report findings and issues to the program - Agencies will work with the program to resolve issues or defects
|  | Readiness | Overall system and operational readiness. | 1 - Create readiness plan that will in include final validation before code is deployed to production | 1 - Agencies will perform final readiness testing to validate code is ready for production deployment 2 - Along with the program readiness activities, agencies will be responsible for creating their own internal deployment and communications plans

## Overview
One Washington is a comprehensive, business transformation program to modernize and improve aging administrative systems and related business processes that are common across state government. There are four key business areas with change management touching all areas.

## Wave Info
Wave 1
OFM
Governor’s Office
WaTech
DES (+ small agencies except for Payroll only)
DOC
Services for the Blind
Treasurer
DOH
UTC
UW (*Integration only)
Full Deployment or Wave 2
All remaining agencies
Expanded Functionality or Wave 3 *Reserved for agencies that require expanded functionality to meet their business needs. Currently only Grantor Management and Inventory Management have been identified.
Currently only 2 agencies use Grantor and Inventory management