## Sheet1
We have provided Due Dates (blue/italicized are our suggestions); many of these tasks can, and should, be started WELL before the due dates
Not all tasks will apply to every agency
Category | Task | Due Date | Person Responsible | Completion Date | Notes/Resources/References
PHYSICAL INVENTORY | Send instructions out for physical inventory | 2025-04-30 |  |  | SAAM 30.45. Must be done at least every other year and must be complete by 6/30
PREPARATION | Identify unliquidated accruals from prior fiscal years; liquidate as needed prior to FM close | 2025-04-30 |  |  | SAAM 90.25.45
PREPARATION | Send "end of fiscal year" instructions to all staff | 2025-04-30 |  |  | Deadlines for submitting travel, invoices, etc.
PREPARATION | Have staff sign-up for year-end trainings (late May and June) | 2025-05-01 |  |  | Fiscal Year-End Workshop
PREPARATION | Complete fiscal year-to-date GL reconciliations and make corrections | 2025-05-31 |  |  | General Ledger Reconciliation Resource Site
PREPARATION | Review user access to accounting systems and update as necessary | 2025-05-31 |  |  | i.e. AFRS, CAMS, TEMS
PREPARATION | Ensure In-Process (71xx), GL 9920, and AFRS error files are cleaned-up. | 2025-06-30 |  |  | Focus: Prior to cash cut-off; Use Unbalanced In-Process Report & Clearing Account Review (GL 9920)
PREPARATION | Complete any transfers, including expenditure transfers between funds. | 2025-06-30 |  |  | Focus: Prior to cash cut-off
PREPARATION | Clear Account 01P - Suspense Account activity | 2025-06-30 |  |  | Focus: Prior to cash cut-off; Use Agency Trial Balance to identify balances
LEASE/SBITAs | Ensure DebtBook has been updated with FY25 changes (i.e. new leases/SBITAs, changes/amendments to existing contracts, allocation changes) | 2025-06-30 |  |  | Training on Leases, SBITAs, and PPPs Resource Site
PHYSICAL INVENTORY | All inventory counts must be completed | 2025-06-30
IMPORTANT DATE: CASH CUT-OFF (link provides cutoff dates for specific transaction types) |  | 2025-06-30 |  |  | OST FY25 Cash Cut-Off Memo
GENERAL | Have a process to ensure correct fiscal month is being used on all transactions (FM24, 25, or 01) | 2025-07-01 |  |  | *Revenue and expenditures/expenses should be recognized in the period the goods or services are provided or received (June 30, 2025 is the cut-off date for FY25) *Checks dated 6/30/25 or earlier are still considered received in FY25 *Interagency payment date is the date cash is credited/posted to receiving agency by OST (agencies that receive EFTs will have a two-day lag) *Accrue FY25 invoices in FM24/25 - cash will go out in FM01
EXCEPTIONS | Schedule and begin to clear/review exception reports: | 2025-07-01 |  |  | Enterprise Reporting Website
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Accounting | 2025-07-01
EXCEPTIONS | Agency Trial Balance | 2025-07-01 |  |  | Review for reasonableness; ensure that fund balance GL codes are appropriate (SAAM 90.20.62)
EXCEPTIONS | Depreciation Expense and Increase in Allowance for Depreciation Review | 2025-07-01 |  |  | Difference should be zero
EXCEPTIONS | Estimated Accrued Expenditures/Expenses (GL 6560) Review | 2025-07-01 |  |  | Review for reasonableness
EXCEPTIONS | Merchandising Activity - Proprietary Accounts | 2025-07-01 |  |  | Agencies w/merchandise inventory (14**) should also have revenue and expenses
EXCEPTIONS | Prior Period Adjustment Activity (04/85; 04/86) | 2025-07-01 |  |  | Review for reasonableness; debit activity generally not allowed
EXCEPTIONS | Transfers | 2025-07-01 |  |  | Difference should be zero. 06/21 activity should be a credit. 06/22 and MB activity should be a debit
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Accounting --> Budget/Actuals | 2025-07-01
EXCEPTIONS | Appropriations Overspent | 2025-07-01 |  |  | Report MUST be cleared
EXCEPTIONS | Appropriations Versus Actuals | 2025-07-01 |  |  | Review for reasonableness; Appropriations not used that should have been; no negative expenditures
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Accounting -->Exceptions | 2025-07-01
EXCEPTIONS | Clearing Accounts Review (GL 9910 and 9920) use prior year criteria | 2025-07-01 |  |  | Difference should be zero at the GL/Document#/Account level
EXCEPTIONS | Consumable Inventory for Governmental Accounts | 2025-07-01 |  |  | Difference should be zero
EXCEPTIONS | COPs and Capital Leases - Governmental Accounts | 2025-07-01 |  |  | Difference should be zero or have an explanation why it doesn't
EXCEPTIONS | Encumbrances - First Fiscal Year Operating (GL 6410) | 2025-07-01 |  |  | Must be clear at year-end
EXCEPTIONS | Encumbrances by Account and Program | 2025-07-01 |  |  | Must be clear at biennium-end
EXCEPTIONS | Expense Elimination for Proprietary Accounts | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | General Ledger Accounts with Unchanged Balances | 2025-07-01 |  |  | Items not clearing must have an explanation; ; Run with Option B selected to show exceptions at the GL Subsidiary level
EXCEPTIONS | Long-Term Receivables/Payables for Governmental Accounts | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Major Source 09 (Non-Revenue) to be Redistributed | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Object S Debit Exceptions | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Object T Elimination | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Object T For Proprietary Accounts | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Objects SZ and TZ Not Redistributed | 2025-07-01 |  |  | Must be clear
EXCEPTIONS | Private/Local Revenue/Expenditures | 2025-07-01 |  |  | Revenues must be greater than or equal to expenditures
EXCEPTIONS | Questionable Balance - Assets and Deferred Outflows of Resources | 2025-07-01 |  |  | Must be clear; Run with Option B selected to show exceptions at the GL Subsidiary level
EXCEPTIONS | Questionable Balance - Liabilities and Deferred Inflow of Resources | 2025-07-01 |  |  | Must be clear; Run with Option B selected to show exceptions at the GL Subsidiary level
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Accounting --> Federal | 2025-07-01
EXCEPTIONS | Federal Revenues and Expenditures | 2025-07-01 |  |  | Revenues generally should equal expenditures
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Accounting --> Interagency and Interfund | 2025-07-01
EXCEPTIONS | Interagency Payables | 2025-07-01 |  |  | Differences should be zero
EXCEPTIONS | Interagency Receivables | 2025-07-01 |  |  | Differences should be zero
EXCEPTIONS | Interfund Receivables/Payables | 2025-07-01 |  |  | Differences should be zero
EXCEPTIONS | Pooled Cash & Investments Due To/From Other Funds (GL 1355 & 5155) | 2025-07-01 |  |  | Differences should be zero
EXCEPTIONS | ER Reports --> Public Folders --> Financial Reports --> Administering Agency | 2025-07-01
EXCEPTIONS | Administering Agency Trial Balance | 2025-07-01 |  |  | See above, just from the admin agency perspective
EXCEPTIONS | Questionable Balance - Assets and Deferred Outflows of Resources | 2025-07-01 |  |  | See above, just from the admin agency perspective
EXCEPTIONS | Questionable Balance - Liabilities and Deferred Inflow of Resources | 2025-07-01 |  |  | See above, just from the admin agency perspective
IMPORTANT DATE: Disclosure form application opens |  | 2025-07-07
DISCLOSURES | Test disclosure form application access and verify appropriate staff have access and can get into system. | 2025-07-08 |  |  | Disclosure Form Application website
IMPORTANT DATE: FM24 Closes |  | 2025-07-15
GENERAL | Update GL reconciliations through FM 24 close | 2025-07-16 |  |  | General Ledger Reconciliation Resource Site
INTERAGENCY | Send out all interagency billings (these can be estimated charges or actuals) for services rendered through June 30 | 2025-07-24 |  |  | If billing agency does not meet the deadline, the liability will be recognized in FY26.
IMPORTANT DATE: Interagency billings mailed |  | 2025-07-24
GENERAL | Verify Capital Asset Management System (CAMS) is up-to-date for any FY25 activity (acquisitions, disposals, and impairments) | 2025-07-31 |  |  | Capital Asset Management System (CAMS) website
GENERAL | Complete all revenue and expenditure accruals | 2025-07-31 |  |  | Pay close attention to transactions involving cash and set up interfund payables/receivables appropriately
IMPORTANT DATE: Phase 1 closes |  | 2025-07-31
GENERAL | Complete year-end adjusting entries: | 2025-08-22
LEASE/SBITAs | Record FY25 lease and SBITA entries from DebtBook | 2025-08-22 |  |  | Resource on Leases, SBITAs, and PPPs Resource page
GENERAL | Record Debt Activity (COP and/or BONDS) | 2025-08-22
GENERAL | Record compensated absence accruals | 2025-08-22 |  |  | Agencies will receive memo from OFM (normally around 2nd week of August)
GENERAL | Record capital asset entries for FY25 CAMS agencies use CM810 and CM820 reports) | 2025-08-22 |  |  | Capital asset AFRS transaction codes for governmental and proprietary accounts
GENERAL | Record FY25 Construction in Progress Activity | 2025-08-22 |  |  | Add FY25 costs that need to be capitalized; Reclassify assets placed in service/sompleted to the appropriate asset GL account
GENERAL | Record inventory balance adjustments | 2025-08-22 |  |  | Exception Report: Consumable Inventory for Governmental Accounts and SAAM 85.56
GENERAL | Record Unavailable Revenue adjustments for portion of receivables that won't be collected in the next 12 months. | 2025-08-22 |  |  | Refer to Subsections 85.70.40, 85.70.45, and 90.20.20.
GENERAL | Record pollution remediation obligation adjustments | 2025-08-22
GENERAL | Record any other annual liability adjustments not already mentioned (short-term/long-term AND actuarial) | 2025-08-22
GENERAL | Liquidate encumbrances | 2025-08-22
GENERAL | Ensure Account 01P - Suspense balances have been distributed | 2025-08-22 |  |  | Agency Trial Balance for Account 01P Note: Account 01P is a Fiduciary Fund and therefore, no interfund payable/receivable balances can be recorded in it. There are special instructions for clearing 01P after cash cut-off.
GENERAL | Ensure Revenue Major Source 09 balances have been distributed | 2025-08-22 |  |  | Exception Report: Major Source 09 (Non-Revenue) To Be Distributed and SAAM 90.20.70.b.
GENERAL | Reconcile federal revenues and expenditures and record a receivable for expenditures not yet reimbursed for or record unearned revenue for any grant money received, but corresponding expenditures have not been incurred. | 2025-08-22 |  |  | Exception Report: Federal Revenues and Expenditures
EXCEPTIONS | Continue working to clear all exceptions (see list above) | 2025-08-22
INTERAGENCY | Interagency Payables/Receivables must be balanced | 2025-08-22 |  |  | Exception Reports: GL03-Interagency Payables and GL04-Interagency Receivables
DISCLOSURES | State Disclosure Forms |  |  |  | See State Disclosure Forms training on SWA Training Website
DISCLOSURES | Complete Bond Debt by Major Class - Summary of Activity Disclosure | 2025-08-22
DISCLOSURES | Complete Bond Sales Disclosure | 2025-08-22
DISCLOSURES | Complete Debt General Disclosure | 2025-08-22
DISCLOSURES | Complete Cash and Investments General Disclosure | 2025-08-22
DISCLOSURES | Complete Cash and Investments Restricted Disclosure (required) | 2025-08-22
DISCLOSURES | Complete Cash on Hand and in Bank Disclosure | 2025-08-22
DISCLOSURES | Complete Certificates of Deposit (Non-negotiable) Disclosure | 2025-08-22
DISCLOSURES | Complete Certificates of Participation Disclosure - Agencies | 2025-08-22
DISCLOSURES | Complete Certificates of Participation Disclosure - OST | 2025-08-22
DISCLOSURES | Complete Internal Control/Internal Audit Questionnaire Disclosure (required) | 2025-08-22
DISCLOSURES | Complete Miscellaneous Disclosure (required) | 2025-08-22
GENERAL | Submit Pollution remediation site status report | 2025-08-22
GENERAL | Submit Asset retirement obligation report | 2025-08-22
DISCLOSURES | Federal Disclosure Forms | 2025-08-22 |  |  | Official due date is 9/5, but asking agencies to complete by phase 1B if possible.
DISCLOSURES | Complete Federal Analytical Review | 2025-08-22 |  |  | See Federal Disclosure Forms training on SWA Training Website
DISCLOSURES | Complete Federal Assistance Received from Nonfederal Sources (Pass-Through) | 2025-08-22
DISCLOSURES | Complete Federal Financial Assistance - Direct | 2025-08-22
DISCLOSURES | Complete Federal Identification Numbers | 2025-08-22
DISCLOSURES | Complete Federal Loan Balances | 2025-08-22
DISCLOSURES | Complete Federal Nonfinancial Assistance | 2025-08-22
DISCLOSURES | Complete Federal Nonfinancial Assistance Inventory Balances | 2025-08-22
IMPORTANT DATE: Phase 1B closes |  | 2025-08-22
EXCEPTIONS | Ensure all exceptions have been cleared (see list above) | 2025-09-05
GENERAL | All remaining AFRS adjustments must be complete | 2025-09-05 |  |  | Pay close attention to transactions involving cash and set up interfund payables/receivables appropriately
GENERAL | Update GL reconciliations with final FY25 balances and activity | 2025-09-05
DISCLOSURES | State Disclosure Forms | 2025-09-05 |  |  | See State Disclosure Forms training on SWA Training Website
DISCLOSURES | Complete Capital Assets - Summary of Activity Disclosure | 2025-09-05
DISCLOSURES | Complete Inventory Disclosure | 2025-09-05
DISCLOSURES | Complete Lease and SBITA Disclosure (required) | 2025-09-05
DISCLOSURES | Complete Liabilities by Major Class - Summary of Activity Disclosure | 2025-09-05
DISCLOSURES | Complete Long-Term Construction Commitments Disclosure | 2025-09-05
DISCLOSURES | Complete Pension Disclosure - DRS | 2025-09-05
DISCLOSURES | Complete Pension Disclosure - Higher Education | 2025-09-05
DISCLOSURES | Complete Taxes Receivable Disclosure | 2025-09-05
DISCLOSURES | Complete Transfer Disclosure | 2025-09-05
DISCLOSURES | Complete Unavailable and Unearned Revenues Disclosure | 2025-09-05
DISCLOSURES | Federal Disclosure Forms must be completed | 2025-09-05 |  |  | See Federal Disclosure Forms training on SWA Training Website
IMPORTANT DATE: Phase 2 closes |  | 2025-09-05 |  |  | No more AFRS entries in FY25. If anything material is found, contact OFM Statewide Accountant ASAP
GENERAL | Have staff available to answer questions from OFM about disclosure forms and correct as needed. | 2025-09-17
GENERAL | Identify if your agency has any required attachments and submit with your certification | 2025-09-17 |  |  | Examples: pollution remediation site status report, narrative related to a Service Organization Control (SOC) report, certification related to the use of a specialist
CERTIFICATION | Submit completeted GL Reconciliation Certification form (required) to OFMAccounting@ofm.wa.gov | 2025-09-17
CERTIFICATION | Submit completed State disclosure certification (required) to OFMAccounting@ofm.wa.gov | 2025-09-17
IMPORTANT DATE: State disclosure certification form & GL reconciliation certification form due |  | 2025-09-17 |  |  | Download certification from Disclosure Form Application
GENERAL | Liquidate any remaining interfund receivable and payable accruals from year-end in FY26 using TCs 025 and 026. | 2025-10-31 |  |  | See FY25 biennium end reference guide on SWA Year-End Closing Site
GENERAL | Track accruals and reverse/liquidate appropriately in the new fiscal year | 2025-10-31
GENERAL | Complete a lessons learned with staff | 2025-10-31 |  |  | What went well, what processes need to change for next year, and what can we work on this year to make next year smoother?
CERTIFICATION | Complete the Federal assistance certification and send to OFMAccounting@ofm.wa.gov | 2026-02-27
IMPORTANT DATE: Federal assistance certification form due |  | 2026-02-27