## Timeline
Timeline for 2025 to 2027 AFRS Table Roll and Related Activities
When | Who | Action Required
By mid-March | OFM-SWA | Send email to table roll contacts and post documents to table roll webpage.
April 1 by close of business (COB) | Agencies who want to opt out | To opt out of ANY phase of the table roll, send an email specifying tables you do NOT want rolled to HereToHelp@ofm.wa.gov. (Refer to User Guide for specific instructions.)
April 1 (COB) | Agencies | Verify/update AFRS report request for table roll reports – refer to User Guide document.
April 1 (COB) | OFM-SWA | Send email on behalf of any closed agencies to HereToHelp@ofm.wa.gov to not roll their tables.
April 3 (COB) | OFM-ITS | Update control table, per agency requests. Send confirmations to agencies.
April 3 (COB) | Agencies who want to opt out | Verify correct tables are marked to not roll on AFRS Biennium Table Roll screen (TM.3.8).
April 7 | OFM-ITS | Run SIMULATED Phase 1 Roll (OI/DT).
April 7 – 18 | Agencies | Review OI simulated roll report (DWP850IC) and correct records, as needed, before Phase 1 actual roll.
April 19 | OFM-ITS | Run ACTUAL Phase 1 Roll (OI/DT).
April 21 (begin) | Agencies | Review and update Phase 1 tables (BI 27).
April 21 - 25 | OFM-Budget | Update D27-Statewide Program table (BI 27) prior to Phase 2.
April 28 | OFM-ITS | Run SIMULATED Phase 2 Roll (PI and related).
April 28 - May 9 | Agencies | Review PI simulated roll reports (DWP850PI and DWP85065) and correct records, as needed, before Phase 2 actual roll.
May 10 | OFM-ITS | Run ACTUAL Phase 2 Roll (PI and related).
May 12 (begin) | Agencies | Review and update Phase 2 tables (BI 27).
May 27 | OFM-ITS | Run SIMULATED Phase 3 Roll (AI and related) - see Notes.
May 27- June 7 | Agencies | Review AI simulated roll reports (DWP850AI, DWP85072, and DWP85093) and correct records, as needed, before Phase 3 actual roll.
June 7 | OFM-ITS | Run ACTUAL Phase 3 Roll (AI and related).
June 9 (begin) | Agencies | Review and update Phase 3 tables (BI 27).
June 14 | OFM-ITS | Run ACTUAL Phase 4 Roll (CAS tables).
Prior to June 30 | Agencies | FINAL Review and update of ALL tables.
Notes:
The simulated Phase 3 (AI) roll, scheduled for May 27, will only be run if the new D26 Expenditure Authority Schedule (BI 27) is available. Phase 3 may be run more than once. Refer to Table Roll User Guide document for more information about the Phase 3 Roll and contingency plans.
OFM-ITS will send reminders via GovDelivery emails 2-3 business days before due dates. To receive emails, ensure you are signed up for the topic: AFRS.